## M1
CCO eCoaching Log
Schedule
| Planned milestone finish date |  | 2015-07-31 |  | M1 iteration completed. June 1 - July 31
| Actual/Forcast milestone finish date |  | 2015-07-31
| Milestone % Complete |  | 100%
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed | System change requested by the program had unintended consequences. Code was changed to reflect how it was previously. Note: Prior iteration data not available in TFS.
| Critical | 0 | 0 | 0 | 0
| High | 0 | 0 | 0 | 0
| Medium | 1 | 0 | 0 | 0
| Low | 0 | 0 | 0 | 0
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0! | No peer reviews were performed in this period.
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
| Critical | 3 | 3 | 0 | 0
| High | 1 | 1 | 0 | 0
| Medium | 7 | 6 | 0 | 0
| Low | 0 | 0 | 0 | 0
Effort
|  | Project |  | CLIN
|  | Iteration to date | YTD |  |  | Analysis
| Iteration Bid | 771 | 771 | 1719 |  | Doug Stearns spent consierable time on the OAR project. Multiple projects use the same CLIN and resources are shared across numerous projects. The program manager has been kept up to date on resource reassignment. Work assigned to this resource will be addressed in M2 as work on the OAR project moves into a development phase.
| Iteration Forecast | 800.6 | 800.6 | 1009
| Iteration Actual | 590.7 | 590.7 | 960
| Variance(forcast - actual) | 209.9 | 209.9 | 49
| Bid Variance | 180.3 | 180.3 | 759
Cost
|  | Iteration to Date | YTD | CLIN YTD
| Bid | 61081.85 | 61081.85 | 151826.54 |  | Cost variance also reflects the use of eCL resources on OAR after mid-june. CLIN data is presented as this CLIN is used by several projects.
| Actual | 47536.84 | 47536.84 | 89450.14
| Variance | 13545.01 | 13545.01 | 62376.4

## M2
CCO Assignment and Exception Tracking System Measurements
Schedule
| Planned milestone finish date |  | None |  | The A&E system does not currently have any milestone targets.
| Actual/Forcast milestone finish date |  | None
| Milestone % Complete |  | N/A
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
Critical
High
Meduim
Low
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0!
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
| Critical | Open | Closed | Open | Closed
High
Meduim
Low
Effort
|  | Iteration to date | Variance | YTD | Variance | Analysis
Iteration Bid
Iteration Forecast
Iteration Actual

## M3
CCO Assignment and Exception Tracking System Measurements
Schedule
| Planned milestone finish date |  | None |  | The A&E system does not currently have any milestone targets.
| Actual/Forcast milestone finish date |  | None
| Milestone % Complete |  | N/A
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
Critical
High
Meduim
Low
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0!
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
| Critical | Open | Closed | Open | Closed
High
Meduim
Low
Effort
|  | Iteration to date | Variance | YTD | Variance | Analysis
Iteration Bid
Iteration Forecast
Iteration Actual

## M4
CCO Assignment and Exception Tracking System Measurements
Schedule
| Planned milestone finish date |  | None |  | The A&E system does not currently have any milestone targets.
| Actual/Forcast milestone finish date |  | None
| Milestone % Complete |  | N/A
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
Critical
High
Meduim
Low
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0!
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
| Critical | Open | Closed | Open | Closed
High
Meduim
Low
Effort
|  | Iteration to date | Variance | YTD | Variance | Analysis
Iteration Bid
Iteration Forecast
Iteration Actual

## M5
CCO Assignment and Exception Tracking System Measurements
Schedule
| Planned milestone finish date |  | None |  | The A&E system does not currently have any milestone targets.
| Actual/Forcast milestone finish date |  | None
| Milestone % Complete |  | N/A
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
Critical
High
Meduim
Low
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0!
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
| Critical | Open | Closed | Open | Closed
High
Meduim
Low
Effort
|  | Iteration to date | Variance | YTD | Variance | Analysis
Iteration Bid
Iteration Forecast
Iteration Actual