# CCO eCoaching Log

# Software Project Plan

June 11, 2015

Revision History

| Version | Date | Author | Comments |
| --- | --- | --- | --- |
| 3.0 | 6/11/2015 | Timothy Queen | Initial version for OY3 based on OY2 |
| 3.1 | 7/8/15 | Timothy Queen | Updated for JKH comments |

Table of Contents

1	Introduction	5

2	Project organization	5

3	Project measurements	7

4	Project milestones and objectives	12

4.1	Iterations	12

4.2	Documentation Updates	14

5	Stakeholder plan	14

6	Project Security Plan	19

7	Tools and environment	21

System Environment	21

8	Work Product Reviews	24

8.1	Peer Review Selection and Approach	24

8.2	Verification and Validation	24

8.2.1	Verification Methods	24

8.2.2	Validation Activities	24

9	Formal Decision Approach	25

10	Project Training Plan	25

11	Deployment	27

11.1	Maintenance	27

11.2	New Development	28

12	Lessons learned	28

13	Governance Plan	28

14	Software Configuration Management Plan	43

15	Lifecycle Selection	43

# Introduction

The eCoaching log (eCL) project plan will provide a high-level overview of the project and will serve as the formal document used to execute the requirements of the eCL application and input from the project stakeholders. The project plan will document our approach and methodology used by the eCL Engineering team.

The eCL is designed to provide feedback to CSRs of the Contact Center Operations (CCO), including alternate channels (e.g. Web Chat, ARC, Written Correspondence), Supervisors, LSA, Quality Specialists and Trainers. The eCoaching Log builds on our goal of continuous improvement to achieve sustainable results.

Supervisors and Managers submit eCLs for an individual to correct unfavorable behavior. They submit eCLs through a front-end Internet application which gets delivered to the individuals manager for coaching. Depending on the type of coaching required, both Supervisor and Manager could be required to review and sign-off.

Multiple feeds exist for the eCL application:

- Outlier data to identify coaching opportunities.

- IQS feed (via LimeSurvey®)  and Verint.

- PeopleSoft

- Aspect

The eCoaching Log contains a component for individuals to have the ability to comment on, or simply acknowledge the coaching comments entered by the supervisor or manager. The eCoaching Log establishes consistency and ease of use in our coaching notes process along with providing historical coaching data for all individualss.

During this option year, several enhancements are planned to provide more functionality to the eCL system.  These enhancements will be done through SCRs if they are minor in nature.  Larger enhancements will be documented in this plan as they arise.

# Project organization

- Tim Queen is the Software Project Manager for the eCoaching Log and works out of the Lawrence office.  He will be creating weekly status reports and holding weekly touch-base meetings with the eCoaching Log Program Leads.

- Susmitha Palacherla is the database developer and works remote out of her Atlanta, Georgia home office.  Her role will be to support database and ETL.

- Dave Hinman is a senior developer who works out of the Coralville, Iowa office.  His role will be to support database, ETL and back-up Suzy.

- Lili Huang is the web developer who works out of the Coralville Iowa office.  Her role will be to support web development.

- Doug Stearns is a requirements and test engineer who works out of the Coralville, Iowa office.  His role will be to support testing and requirements.

As indicated above, the eCL project interacts with the Interface to Quality Systems (IQS), Verint and the LimeSurvey® scorecard system. These systems provide the results of monitoring of CSR in the CCO.  Dave Hinman is the lead developer on the IQS.

# Project measurements

| Organizational Standard Metrics |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Information Need | Measurement | Resp. Role | Analysis Method | Analysis and Reporting Frequency | Source |  | Where Data and Results are Stored | Who Receives Data |
| Effort/Cost |  |  |  |  |  |  |  |  |  |
| Manage project effort to commitments from the Proposal/BOE. | Compare planned effort with actual effort: • Are we delivering to our plan? • How accurate are our estimates? • Are we delivering to our estimates? • Are certain tasks or activities taking more/less effort than expected? • How much effort will it take to perform project activities? | Actual effort variance to plan effort ((Actual effort – plan effort)/plan effort) * 100 Percentage over or under plan Iteration trends | Project Manager | Understanding how estimates compare to actual results is a key measure of project progress in meeting commitments. Establishing a trigger to alert management and the project team when corrective actions are needed enables project teams to realize the full benefit of this metric. Corrective action should be taken when actual variance to plan effort exceeds a threshold of +/- 10%. | Iteration | ETS |  | Data is stored in Oracle. Reports and analysis results are stored in location specified in CI/DI list. | Project Manager Program Manager |
| Manage the project to meet or exceed commitments from the Proposal/BOE and sector financials. | To provide insight into planned and or estimated cost compared to expended cost on projects: • How accurate are our estimates? • Are we delivering to our estimate? • Are we delivering to our plan? • How much cost will it take to perform project activities? | Actual cost variance to plan cost ((Actual cost – plan cost)/plan cost) * 100 Percentage over or under plan Iteration trends | Program Manager | Understanding how cost estimates compare to actual results are a key measure of project progress in meeting project commitments and give project and program managers and teams the ability to take corrective actions. Corrective action should be taken when actual variance to plan effort exceeds a threshold of +/- 10%. Analysis and understanding of this data over time will also help to improve the accuracy of future estimates. | Iteration | N/A |  | Data is stored in CostPoint. Reports and analysis results are stored on project SharePoint site (furnish url) | Project Manager Program Manager |
| Schedule |  |  |  |  |  |  |
| Provide insight into schedule variation from plan and progress to achieving milestones. | • Deliver on our commitments. • Meet deadlines. • We deliver to our estimates. • Control costs. | Planned milestone finish date Record during project and/or iteration planning | Project Manager | Projects behind schedule typically require some sort of corrective action. Projects ahead of schedule may want to consider releasing committed resources that are no longer needed back to the organization. | Iteration | MS Project |  | Data is stored in MS Project Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Provide insight into schedule variation from plan and progress to achieving milestones. | • Deliver on our commitments. • Meet deadlines. • We deliver to our estimates. • Control costs. | Actual/Forecast milestone finish date Record during project execution | Project Manager |  | Ongoing | MS Project |  | Data is stored in MS Project Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Provide insight into schedule variation from plan and progress to achieving milestones. | • Deliver on our commitments. • Meet deadlines. • We deliver to our estimates. • Control costs. | Milestone % Complete Record during iteration while executing iteration plan | Role or individual responsible for a given milestone |  | Ongoing | MS Project |  | Data is stored in MS Project Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Quality |  |  |  |  |  |  |
| Provide insight into the quality of the system/solution to be delivered. | Are we delivering a quality product? • How many problem reports have been opened? • What are their severities? | Number of defects by severity Count all defects by their severity code Possible representation: Stacked vertical bar graphs illustrate the relative weighting of defect severity types | Project Manager | • Are most of the defects being found critical with severe system impacts, or relatively minor? • Is severity trending upward or downward? • Are there particular areas of the system/software with larger quality issues than others? | As needed and determined by the project | TFS |  | Data is stored in TFS Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Provide insight into the quality of the system/solution to be delivered. |  | Open vs. Closed Defects All SCRs of type Problem Report and Status = Open compared to all SCRs of type Problem Report and Status = Closed Possible representation: Trend graph over time (e.g., by iteration) | Project Manager | Are defects being opened faster than they are being closed? • Are we opening more or fewer defects this iteration than last? Answers to these questions are good indicators for project managers and team members of how the project’s quality profile is progressing. | As needed and determined by the project | TFS |  | Data is stored in TFS Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Evaluate the effectiveness of defect detection through the project lifecycle. | How effective are peer reviews at removing defects? • How much time is spent on peer reviews? • How many defects per effort hours are discovered during peer reviews? • What types of work products undergo peer review? • Are we delivering a quality product? | Peer Reviews Project Name Work Product Type - Architecture - Design - Code - Project Management - Requirements - Testing - Other (specify your own value) Phase/Iteration ID Number of Defects Total effort (hours) Number of reviewers Effort per defect found = (Total hours / Number of Defects) | Project Manager | Analyze the project's defect discovery rate (I.e., Effort per defect found) and determine if the rate meets the projects needs and expectations. | As needed and determined by the project | Peer Review Selected Work Products |  | Peer Review Measurements | Project Manager |
| Provide insight into requirements stability | • How many change requests have been opened? • How many change requests are currently open? | Open vs. Closed Change Requests All SCRs of type Change Request and Status = Open compared to all SCRs of type Change Request and Status = Closed | Project Manager | • Are change requests being opened faster than they are being closed? • Are we opening more or fewer change requests this iteration than last? Answers to these questions are good indicators for project managers and team members of how stable project requirements are. Requirements are typically not stable initially as the team collaborates with customers and other stakeholders to derive customer requirements. However, requirements that are continually changing too far into the SDLC may impact milestone dates and product quality. | As needed and determined by the project | TFS |  | Data is stored in TFS Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |

| Project Specific Metrics |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Information Need | Measurement | Resp. Role | Analysis Method | Analysis and Reporting Frequency | Source | Where Data and Results are Stored | Who Receives Data |
| None |  |  |  |  |  |  |  |  |

The eCoaching Log, Assignment and Exception Tracking System and Report Automation systems are bid as one under the CCO contract.  They use the same charge code and may share resources.

# Project milestones and objectives

Project Milestones and objectives will be tracked in the project management schedule and Kanban. The Microsoft Project schedule is located here:

- http://vmsps2010app01/PWA/Project%20Detail%20Pages/Schedule.aspx?ProjUid=f8e8a3cb-de6f-4c48-b74a-dfc1dd2f9efa

## Iterations

All minor changes related to the system will be identified and worked with the Software Change Request process. This may include but is not restricted to security changes, new reports, new data feeds, database and user interface updates.

| Iteration | Primary objectives (risks and use case scenarios) | Scheduled start or milestone | Target velocity |
| --- | --- | --- | --- |
| M1 | Maintenance Iterations M1-5 Objectives: - SCRs as needed - Planned system changes - Performance improvements - Additional job codes - Coaching record deletion - Data export - Duplicate Lan IDs - Notes overwritten - Leave of absence - Security and system patching - Issue Log research and resolution | 6/1/2015 – 7/19/15 | 15 |
| M2 | - SCRs as needed - Planned system changes - CSR Survey – This is creating a survey of the effectiveness and impact of coaching delivered by supervisors to CSRs. - Inactivation – Inactivation of eCL and warning records. - Reassignment – Reassignment tool to assist with hierarchy changes - Scorecard Mapping – Update the feed to the eCL due to changes in the Verint evaluation form. - Carriage Return – Include carriage return in the body of the coaching description. - Verint Source QA and Sup – Add granularity to Verint GDIT by separating evaluations completed by Quality and CCO - Security and system patching - Issue Log research and resolution | 7/20/15-9/1/15 |  |
| M3 | - SCRs as needed - Planned system changes - Tickler on Coaching SLA – Add email notification for records are sit on pending status. - Add warning segment – Add the warning section on all modules. - eCL Sandbox – Develop a sandbox for demo / presentation. - Open CSR comment field – Open the CSR comment field on all types of eCL. Capture the comments of employees when reviewing and acknowledging records. - Security and system patching - Issue Log research and resolution | 9/2/15 – 12/31/15 |  |
| M4 | - SCRs as needed - Security and System patching - Issue Log research and resolution | 1/4/16 – 3/31/16 |  |
| M5 | - SCRs as needed - Security and System patching - Issue Log research and resolution | 4/1/16 – 5/31/16 |  |

## Documentation Updates

The team will update the following documents as SCRs and new development activities.

| Document | Role |
| --- | --- |
| Functional Specification | Requirements Engineer |
| Trace Matrix | Requirements Engineer Developer Test Engineer |
| Architecture | Developer |
| High Level Design | Developer |
| Detail Design | Developer |
| Code | Developer |
| Unit Test Cases | Developer |
| System Test Cases | Test Engineer |
| Kanban (Work Item List & Iteration Plan) | SPM |
| Lessons Learned | SPM |
| Risk Register | SPM |
| WBS | SPM |

During the OY2 audit, the Trace Matrix was identified as being deficient. Traceability covers requirements and testing only.  Defined process in the tailoring and planning worksheet also includes architecture, design elements and code.  Developers will fill in the missing information for these areas in the trace matrix as they work on new change requests.

# Stakeholder plan

| Role | Assigned Person(s) | Communications Plan | Responsibilities |
| --- | --- | --- | --- |
| *Customer | Scott Mainwaring, Program Vice President Lori Lindstrom, Program Vice President Evan Davis, Senior Director Business Process Improvement and Analytics | email Teleconferences Status Reports | Executive sponsorship for the eCoaching Log Provide requirements for the CCO program |
| *Program Manager | Brian Dye John Tiongson | email Face-to-Face Meetings Teleconferences TFS Weekly project calls | Provide requirements for the CCO program Responsible for the planning, monitoring and controlling the program to ensure that it meets with its business plan goals, and for reporting performance against plan. Serves as communication liaison between the customers, project staff and the development staff. |
| *Tester | Doug Stearns | Email Teleconferences TFS Standup meetings Meetings with SPM | Leads the creation of the Functional Specification and Traceability Matrices Focal point of communication with the customer on issues that arise in the system. Leads the creation of the System Test Plans and Test Cases. Coordinates and participates in the execution of the System Test Plan and cases. For work done within TFS, responsible for the effort, estimate, and testing is all encompassing for the issues being corrected. |
| *SCM Lead | Jackie Miller | Email Teleconferences TFS | Leads all SCM activity. Creates and maintains the SCCB charter. The SCM lead is a member of the SCCB. Facilitates the SCCB meetings Generates the SCCB meeting minutes Provides SCM tool training and support |
| *Project Manager | Tim Queen | Email Teleconferences TFS Standup meetings Weekly meetings with the program 1 to 1 with direct reports Meeting with MGR Document Reviews SharePoint | Develops and updates the project plan Ensures the software development is completed on time and within budget, and serves as contact between project staff and development resources. Responsible for Risk Management and Measurement and Analysis including monthly reporting to senior management and program manager. Responsible for production status and issues Responsible for directing development resources to ensure a quality product from development to production support. Responsible for coordinating the effort between development, testing and business analysts Responsible for formal decision making (DAR) Responsible for project measurement (MA) |
| *Process Auditor | Karen Black | eMail Governance Monthly Report Governance audit plans and reports SharePoint TFS | Objectively evaluating performed processes, work products, and services against the applicable process descriptions, standards, and procedures Identifying and documenting noncompliance issues Providing feedback to project staff and managers on the results of quality assurance activities Ensuring that noncompliance issues are addressed Mentoring projects on process usage |
| *Risk Management | *All project members | Team meetings Weekly team status meetings Document Reviews SharePoint TFS eMail | Participates in monthly risk management review Identifies risks as needed |
| *Validation | eCoaching Log Team | Team meetings Weekly meetings with customer Document reviews SharePoint TFS email | SPM assures that all validation activities are carried out. All team members have the responsibility to identify and report any validation issues. |
| *Project Security Analyst | Brian Szabo | Email Teleconferences TFS | Performs monthly and quarterly scans to ensure compliance. Mentors team on security awareness. Participates in SCCB meetings to provide security oversight and approval. |
| *Developers | Dave Hinman Lili Huang Susmitha Palacherla | email Face-to-Face Meetings Teleconferences TFS Team meetings Bi-Weekly 1 to 1 with SPM | Software development and unit testing Documentation updates Support production operations. |
| *Development Team Lead | Susmitha Palacherla | email Face-to-Face Meetings Teleconferences TFS Bi-Weekly 1 to 1 with SPM | Leads the design effort for the project Leads the coding and unit testing of applications Will be involved in the creation of baselines as well as the baseline audit Responsible for the coordination of development efforts Coordinates the system test and production builds |
| * Stakeholders | Supervisors CSRs Quality Specialists LSAs Trainers HR Contact Center Managers CCO Program Management Senior Management | email Face-to-Face Meetings Teleconferences | Provide requirements for the CCO program Identify any issues with the application Use the software as part of their day-to-day job. |
| Senior Management | Jacquie Haltmeyer John Hess | Weekly 1 to 1 with manager SharePoint TFS Schedule eMail | Responsible for assisting the Program Manager and software project manager with planning, monitoring, and controlling the program to ensure that it meets its business plan goals, and for reporting performance against the plan. Serves as communication liaison between the customers, project staff, and development staff. Breaks down barriers for the team. Helps provide necessary resources while balancing the needs of the CCO program against the business unit. Used as a mentor to help guide the software project manager. |
| Data Feed Providers - High Point Global - LimeSurvey - Aspect - Analytics | SPM – Tim Queen | eMail Teleconferences | Participate in meetings with the team. Provide feedback on requirements. Provide feedback during testing. Coordinate changes in data feed consumer systems that impact team. |

*Required Roles

# Project Security Plan

This is a GDIT initiated application not located on the CCO network and does not store or retain any PHI data.  The eCoaching Log follows GDIT security policies.

The eCoaching Log servers were requested to be built based on the GDIT Windows Server Standard Build, and will follow this standard install for all rebuilds.

The project is requesting a waiver for the creation of the following security documents:

- Application Threat Modeling

- Application Security Risk & Requirements

- Acceptable Risks and Safeguards Audit

This waiver request is to be approved by the program manager.  Acceptance of the plan by the program manager will suffice as acceptance of the waiver request.

The project will perform the following on a case by case basis if the ISSO or GDIT security determines it to be necessary for the work currently being performed by the project.  The project is an internal facing web site.  The system follows Rolls Based Access Controls (RBAC).  No PHI or PII is associated with the system.

| Evaluate code for security | This is to support the assessment of the system implementation against its requirements and within its modeled operational environment by identifying and eliminating source code vulnerabilities and ensuring that source code conforms to established secure coding standards and applicable secure coding guidelines. The four steps to be followed include: Conduct Security Code Review - The Information System Security Officer or approved designee conducts a static code review to ensure conformance to established Secure Coding Standards and applicable Secure Coding Guidelines. Identify Security Risks/Issues - The Information System Security Officer or approved designee identifies issues resulting from the Security Code Review. Resolve Security Risks/Issues - The Software Project Manager (SPM) works with the Information System Security Officer or approved designee to resolve the identified security risks and issues. Update Project Risks/Issues - The SPM reviews any outstanding issues or risks resulting from the Security Code Review and tracks them to resolution on the Global Project Issues List or the project's defect tracking system. |
| --- | --- |
| Evaluate security testing | The purpose is to support the assessment of the system implementation against its requirements and within its modeled operational environment by ensuring the test results sufficiently cover all testable security requirements and to determine whether the software satisfies its security requirements. The four steps to be followed include: Review test results for security coverage - The Information System Security Officer or approved designee analyzes the test results for security coverage. The Information System Security Officer or approved designee identifies issues resulting from the analysis of the test results. - Resolve security risks/issues - The Project Manager or Supplier Agreement Manager work with the Information System Security Officer or approved designee to resolve issues. - Update Project Risks/Issues - The project manager or SAM Manager review any outstanding issues or risks resulting from the test results review and tracks them to resolution. - Approve test results - The Information System Security Officer approves the security test results. |
| Review test activities for security | To support the assessment of the system implementation against its requirements and within its modeled operational environment by ensuring the testing approach planned by the project sufficiently covers all testable security requirements. Four steps to complete: - Review test activities for security coverage - The Information System Security Officer or approved designee reviews the Test Plan to ensure the testing approach planned by the project will sufficiently address all testable security requirements. The Information System Security Officer or approved designee identifies issues resulting from their review of the Test Plan. - Resolve security risks/issues - The project manager works with the Information System Security Officer or approved designee to resolve the identified security risks and issues. - Update project risks/issues - The project manager reviews any outstanding issues or risks resulting from the review and tracks them to resolution. - Approve test planning - The Information System Security Officer approves the planned testing activities. |
| Verify operations security | To ensure that the system is secure in its operational environment. Verify hardware configurations - The Information System Security Officer or approved designee verifies hardware security configurations (e.g., routers, networks, hardware encryption, hardware access, etc.). Verify Software security - The Information System Security Officer or approved designee verifies software configuration and security by reviewing configuration and/or performing security scans. (e.g., account access, security settings, security log settings, etc.). Identify and resolve issues - The Information System Security Officer or approved designee, Program Manager, and Project Manager identify and resolve outstanding issues. Any remaining issues are tracked to resolution ISSO approves for release - The Information System Security Officer approves the system's security settings and configuration |

# Tools and environment

# System Environment

| Process Area | Methodology Standard Used |
| --- | --- |
| Code – SQL Server | Microsoft SQL Server Books Online |
| Code – ETL | The Data Warehouse Toolkit by Kimball and Ross, Wiley Publishing; 2002 The Microsoft Data Warehouse Toolkit by Mundy, Thornthwaite and Kimball, Wiley Publishing; 2006 |
| Code – MDX | MDX Solutions, Second Edition by Spofford, et. al; Wiley Publishing; 2006 |

Development, Test, and Production Environment Software

| Software Requirement | Description |
| --- | --- |
| Computer Resource Requirements | Below are the common software tools used by software projects. Process Section; Tool; Description. Project Management; Microsoft Project 2010; Schedule Management. TFS; Automates Configuration Control. Requirements; Microsoft Word 2010; Create Text. Microsoft Excel 2010; Creates Spreadsheets. Microsoft Visio 2010; Creates Graphics. TFS 6.6.1.19; Automates Configuration Control. Design; Microsoft Word 2010; Create Text. Microsoft Excel 2010; Creates Spreadsheets. Microsoft Visio 2010; Creates Graphics. Architecture; Microsoft Word 2010; Create Text. Microsoft Excel 2010; Creates Spreadsheets. Microsoft Visio 2010; Creates Graphics. Code Other (SQL dev license)- E32-00693-2- Todd (sql Dev License) - MC46H-JQR3C-2JRHY- XYRKY-QWPVM; Visual Studio 2008 SQL Server 2008Express SQL Server Manager Studio 2005 Express Log Parser 2.2 Visual Web Developer 2010 Express SQL Server 2008 Express Toolkit Windows Script Host 5.8; Source Code Editor. Unit/Integration/System Testing; SQL Server 2008 Visual Studio 2008 Shell Beyond Compare 3 Snag it 8.2; Testing Tools. Implementation. SFTP 5.1; Communication. Software Configuration Management / Data Management; TFS; TFS. SharePoint 2010; Data management version control. Applications; Server Installed; License. SQL DB; VRIVFSSDBT02 VDENSSDBP07; Standard. |
| Network Availability Requirements | This project requires no specific network availability considerations beyond the standard network availability provided by the organization. |
| Shared Computer Resources | The project uses virtual database servers for the development and testing environments which are shared environments. |

Computing System Environment

The environments consist of the developers PCs, a virtual web server and virtual database server.  All developers and testers have access to the tools described above.  The following section describes the hardware used in each of the environments.

# Development, Test, and Production Environment Hardware

| Hardware Requirement | Description |
| --- | --- |
| Computer Resources - Production Environment | VDENSSDBP07\SCORP01,1436 – Virtual Database Server owned by the program used for all data storage, retention and transformation of feeds and load data. F3420-MWBP11 – Virtual web server owned by the program used for the web front end |
| Computer Resources – Development and Integration Environment | F3420-MPMD01 – Virtual web server owned by the program used to host the web front end for development. |
| Computer Resources – Testing Environment | F3420-MPMD01 – Virtual web server owned by the program used to host the web front end for testing. |
| Network Availability |  |
| Shared | VRIVFSSDBT02\SCORD01, 1437 – Virtual database server owned by GDIT used for development VRIVFSSDBT02\SCORT01, 1438 – Virtual Database server owned by GDIT used for testing VRIVSCORS01 –Virtual staging server owned by GDIT used to stage and archive source files. |

# Facilities Planning

| Facilities Requirement | Description |
| --- | --- |
| Development | There are no specific facility requirements. |
| Test – Internal | There are no specific facility requirements. |
| Test – Customer Acceptance | There are no specific facility requirements. |
| Production | There are no specific facility requirements. |

# Work Product Reviews

## Peer Review Selection and Approach

The project will perform a peer review of the following items:

- Requirements Document

- Design Document including database structure

The rationale behind doing peer reviews for these components is they have high visibility within the program and are critical to CCO operations.  Peer reviews will be done by members of the development team.

Informal peer reviews will be performed by the team.  One peer review of each document will be performed.

## Verification and Validation

Software verification is ensuring that the product has been built according to the requirements and design specifications, while software validation ensures that the product actually meets the user's needs, and that the specifications were correct in the first place. Software verification ensures that "you built it right". Software validation ensures that "you built the right thing". Software validation confirms that the product, as provided, will fulfill its intended use.

### Verification Methods

Verification is the process of evaluating software to determine whether the products of a given development phase satisfy the conditions imposed at the start of that phase. The eCoaching Log team will use one or more of the following methods to verify the system is working according to specifications prior to software being placed into production.

- Analysis: the processing of accumulated data obtained from other qualification methods.  Examples are reduction, interpolation or extrapolation of test results.

- Demonstration:  the operation of the system, or a part of the system, that relies on observable functional operation not requiring the use of instrumentation, special test equipment, or subsequent analysis.

- Inspection:  the visual examination of system components, documentation, etc.

- Test:  the operation of the system, or a part of the system, using instrumentation or other special test equipment to collect data for later analysis.

- Special qualification methods:  any special qualification methods for the system, such as special tools, techniques, procedures, facilities, acceptance limits, use of standard samples, pre-production or periodic production samples, pilot models, or pilot lots

### Validation Activities

Validation is the process of evaluating software during or at the end of the development process to determine whether it satisfies specified requirements. The Tester will review change requests and test the system to ensure the system works as intended.  Results will be documented in the System Testing logs.  From time to time it may be necessary for the customer to participate in testing.  These results will also be documented.  In either case, if testing identifies defects, the defects must be corrected and retested.

# Formal Decision Approach

The project will follow the Decision Analysis and Resolution process to make formal decisions. Meetings will be established for any DAR activity.  The DAR log will be completed and stored in TFS.

When any of the following criteria are met, this project follows the DAR process.

- Mitigation and contingency planning for a complex risk that has a risk exposure of medium or higher.  Complexity is determined by consensus.

- Decisions which require documentation.

- Solution determination which impacts the project cost by +/-10%.

- Solution determination which negatively impacts the schedule of a critical deliverable.

- Solution determination which impacts Operations performance or SLAs.

# Project Training Plan

GDIT and CCO Annual Required Training

All GDIT employees are required to complete annual Security Awareness and Ethics and Compliance Training available through myLMS. CCO Communications alerts staff to all required training.

CCO Project Training

GDIT retains a wide and diverse group of technical professionals to staff its projects.  Any organizational or specific training and gap analysis is identified and tracked via the Organizational Detailed Training Plan.

Team members working within the identified discipline will require the skills identified below.

| Discipline | Skill | Training Required? | Action to acquire |
| --- | --- | --- | --- |
| General Team Skills | Configuration Management tools (Version Management and defect tracking) | Yes | On the job training for TFS |
|  | Product domain orientation | No |  |
|  | Risk Management | No |  |
|  | Agile Process Library (APL) | Yes | Lili will be taking the HCSD ISE APL classes online |
|  | Risk Management | No |  |
| Requirements | Project’s requirements elicitation, definition and analysis approach | No |  |
|  | Requirements modeling and specification development | No |  |
|  | Understanding of requirements management and tracking | No |  |
|  | Using requirements tools | No |  |
|  | Validation | No |  |
| Architecture\ Development | VB and C# development | No |  |
|  | Software Design | No |  |
|  | System Architecture | No |  |
|  | Integration | No |  |
|  | Unit Testing | No |  |
|  | Secure Coding practices | No |  |
|  | 508 Compliance | No |  |
|  | Defect Tracking and Version Management tools (e.g., TFS) | Yes | Training will be on the job |
| Testing (unit, integration and system) | Using testing tools (list tools as applicable) | No |  |
|  | Creation of test plans, cases, procedures, and scripts | No |  |
|  | Familiarity with <x> testing methodology, test case creation and test case execution | No |  |
| Configuration Management | Planning and documenting an appropriate CM process based on project needs | No |  |
|  | Creation of baselines | No |  |
|  | Release Management | No |  |
|  | In-depth knowledge of configuration management and change tracking tools | No |  |
|  | Leading a configuration control group in all CM activities | No |  |
| Project Management | Solicit, compile, and process estimates for all project development activities | No |  |
|  | Create and manage a software project plan | No |  |
|  | Project Management growth training | Yes | PMI training on GDIT myLMS |
|  | Plan, manage, and report measurement data for project | No |  |
|  | Lead project activities to ensure project is delivered as planned | No |  |
|  | Formal decision making (included in APL) | No |  |
|  | Kanban for Team’s daily work item coordination and communication | No |  |

# Deployment

.

## Maintenance

Once a software configuration change request (SCR) is approved for impact assessment, the SPM assigns the record to the Requirements and Test engineer and developer for their individual assessments.

An SCR is initially deployed in the development environment.  Following successful unit and development testing, the change is promoted into the system test environment by an individual other than the developer.  The promoter role is called the implementer.  The implementer follows the instructions provided by the developer for promotion and implementation.

A successful system test performed by the Test Engineer then routes the change request to be approved for release to the production environment.  Once the SCCB approves to release the SCR to production, the implementer follows implementation instructions to promote to production.

A post-production implementation review is conducted to ensure the software is functioning as expected in the production environment.  This is done by the Test Engineer and a user of the scorecard system.

Configuration items implemented into production are base lined in TFS.

Two types of maintenance activities will be performed (1) Bug fixes and (2) Development/Migration.

Bug fixes will address corrective maintenance which identifies and removes defects and corrects actual errors.  Preventative maintenance will identify and detect latent faults.  Emergency maintenance (critical) to address errors that are causing the system to fail.

Development/Migration will address improvements in performance, dependability and additional functionality.  This will also address upgrades to the environment (hardware, OS, database).

## New Development

Occasionally, software will be developed that will be managed as a project activity and not under a SCR. The work will be initially performed in the development environment. Upon completion of the development, the software will be moved to the test environment. A successful test will result in User Acceptance Testing where the end users will perform testing. The system will be deployed to production upon user approval following implementation instructions.

# Lessons learned

Lessons Learned are added and updated as the project progresses.  The Lessons Learned document can be found in TFS  at this link.  .

The CI/DI List can be found at the same link.

# Governance Plan

The Software Governance activities for this maintenance project are based on the Agile Process Library (APL) process. The resources and dates are identified below.  Minimal SCRs are planned as the work is being tracked under this project and releases will be in phases.

| Audit | Planned Date | Planned Effort | Resources |
| --- | --- | --- | --- |
| Project Plan Review(s) | June 10 – June 20 | 11 hours | Karen Black Jacquie Haltmeyer John Tiongson |
| APL Process Audit | Nov 10 | 21 hours | Karen Black |
| Baseline Audit | October 1 | 4 hours | Karen Black |

The GDIT HCSD Governance Plan can be found at this location. https://spspi.gdit.com/opshcsd/HCSDOPS/HCSDQA/SQA/Shared%20Documents/Forms/Governance%20Plans.aspx

| Audit | Planned Date | Planned Effort | Resources |
| --- | --- | --- | --- |
| Project Plan Review(s) | June 10 – June 20 | 11 hours | Karen Black Jacquie Haltmeyer John Tiongson |
| APL Governance Audit #1 Discipline; Process component; Question or data evaluated; Generic target artifact. SW Project Management; Task; Were required inputs to 'Plan Project' provided to the Project Manager and other planning staff?; APL Compliant Policy Measurements Definitions Standard Project Plan Standard Risk Register Standard Work Items List Standard [Customer Requirements]. SW Project Management; Task; Was a Project Plan created that outlines an initial agreement on how the project will achieve its goals with stakeholder buy-in for starting the project and team commitment?; [Project Plan] Agreement Artifacts. SW Project Management; Task; Were the required outputs to 'Plan Project' created by the Project Manager and Planning Team?; Life Cycle Selection Measurement Definitions Process Waiver Project Plan Risk Register Tailoring and Planning Worksheet Test Plan (optional) Traceability Matrix Work Breakdown Structure Work Items List [Meeting and Review Records]. SW Project Management; Work Product; Does the Measurement Definitions meet the Standard?; Measurement Definitions. SW Project Management; Work Product; Does the Project Plan meet the Standard?; Project Plan. SW Project Management; Work Product; Does the Risk Register meet the Standard?; Risk Register. SW Project Management; Work Product; Does the Work Items List meet the Standard?; Work Items List. SW Project Management; Step; Was Life Cycle Selection performed?; Life Cycle Selection. SW Project Management; Step; Did review and validation of technical scope and estimated size take place with stakeholders?; Work Items List [Estimation Artifacts]. SW Project Management; Step; Has traceability been planned?; Project Plan. SW Project Management; Step; Was a Test Plan created (optional)?; Test Plan (optional). SW Project Management; Step; Were costs established and communicated?; [Cost Estimates]. SW Project Management; Step; Was the process tailored to meet project needs?; Tailoring and Planning Worksheet. SW Project Management; Step; Have Governance activities been planned?; Project Plan. SW Project Management; Task; Were required inputs to 'Plan Configuration Management' provided to the Project Manager and CM Lead?; APL Compliant Policy Configuration Management Plan Standard. SW Project Management; Task; Has the CCB been identified and the CM Plan created, reviewed and placed under configuration management?; [CCB Charter] CM Plan. SW Project Management; Task; Were the required outputs to 'Plan Configuration Management' created by the Project Manager and CM Lead?; CI/DI List CM Plan. SW Project Management; Work Product; Does the Configuration Management Plan meet the Standard?; CM Plan. SW Project Management; Step; Have baseline audits been planned?; CM Plan. SW Project Management; Step; Has the CI/DI List been created and reviewed?; CI/DI List. SW Project Management; Task; Were required inputs to 'Plan Iteration' provided to the Project Manager and project team?; APL Compliant Policy Risk Register Standard Test Plan (optional) Work Items List Standard [Customer Requirements] [Project Plan] [Project Risk] [Project Work]. Architecture; Task; Were required inputs to “Outline the Architecture” provided to the project?; Architecture notebook standard EDD Trace Matrix Customer requirements Technical specification. Architecture; Task; Was there an identification of key architecture elements? Were they documented?; Software Architecture Document and/or Architecture Notebook. Architecture; Task; Were the required outputs to 'Outline the Architecture' created by the project?; Architecture Notebook Decision Log Traceability Matrix [Architecture Review Board Materials]. Architecture; Work Product; Does the Architecture Notebook meet the Standard?; Architecture Notebook. Architecture; Task; Were required inputs to 'Refine the Architecture' provided to project?; Architecture Notebook Architecture Notebook Standard Engineering Design Doc (EDD) Traceability Matrix [Customer Requirements] [Technical Specification]. Architecture; Task; Were the status of Architectural Goals and Significant Requirements reviewed with stakeholders, requirements team, and the team? Was architecture then refined as needed?; Architecture Notebook Traceability Matrix. Architecture; Task; Were the required outputs to 'Refine the Architecture' created by the project?; Architecture Notebook Engineering Design Document Traceability Matrix. Requirements; Task; Were required inputs to 'Develop Technical Vision' provided to project? Vision Standard [Customer Requirements]; Vision Standard [Customer Requirements]. Requirements; Task; Was a vision/solution proposed with collaboration of stakeholders? Was agreement attained?; Vision. Requirements; Task; Were the required outputs to “Develop Technical Vision” created by the project?; Glossary(Optional) Vision. Requirements; Work Product; Does the Vision meet the standard; Vision. Requirements; Task; Were the required inputs to “Identify and Outline Requirements” provided to the project?; System Wide Requirements Standard {Customer Requirements]. Requirements; Task; Were functional and non-functional requirements captured for the system; Requirements Model System Wide Requirements Use Case Specification. Requirements; Task; Were the required outputs to “Develop Technical Vision” created by the project; Glossary(Optional) Requirements Model System Wide Requirements Use Case Specification. Requirements; Work Product; Does the System Wide Requirements meet the Standard?; System Wide Requirements. Requriements; Task; Were required inputs to “Detail Use Case Specifications” provided to the project?; Use Case Standard [Customer Requirements]. Requirements; Task; Were use case specifications in sufficient detail to validate understanding of the requirements, ensure concurrence with stakeholder expectations, and permit software development to begin?; Use Case Specification. Requirements; Task; Were the required outputs to 'Detail Use Case Specifications' created by the project?; Glossary (optional) Requirements Model Traceability Matrix Use Case Specification. Requirements; Work Product; Does the Use Case Specification meet the Standard?; Use Case Specification. Requirements; Step; Were use case specifications updated in the requirements model?; Requirements Model. Requirements; Step; Is requirements traceability maintained?; Traceability Matrix. Requirements; Step; Do stakeholders and project team agree that the detailed use cases and scenarios are consistent with vision?; Meeting Minutes. Requirements; Task; Were required inputs to 'Detail System-Wide Requirements' provided to project?; System Wide Requirements System Wide Requirements Standard [Customer Requirements]. Requirements; Task; Were system-wide requirements in sufficient detail to validate understanding of the requirements, ensure concurrence with stakeholder expectations, and permit software development to begin?; System Wide Requirements. Requirements; Task; Were the required outputs to 'Detail System-Wide Requirements' created by the project?; Glossary (optional) System Wide Requirements Traceability Matrix. Requirements; Work Product; Does the System Wide Requirements meet the Standard?; System Wide Requirements. Requriements; Step; Were system wide requirements updated as they became detailed?; System Wide Requirements. Requirements; Step; Is requirements traceability maintained?; Traceability Matrix. Requirements; Step; Do stakeholders and project team agree that the detailed system wide requirements are consistent with vision?; Meeting minutes. | October 13 | 7 hours | Karen Black Timothy Queen |
| APL Governance Audit #2 Discipline; Process component; Question or data evaluated; Generic target artifact. Configuration Management; Task; Were required inputs to 'Create and Verify Baseline' provided to the CM Lead?; Baseline Package Standard. Configuration Management; Task; Were configuration items identified and approved (CCB) for incorporation into a baseline?; Baseline Audit Plan & Report Baseline Package. Configuration Management; Task; Were the required outputs to 'Create and Verify Baseline' created by the CM Lead?; Baseline Audit Plan & Report. Configuration Management; Work Product; Does the Baseline Package meet the Standard?; Baseline Package. Configuration Management; Step; Was the baseline objectively examined to verify its integrity against the Iteration Plan Configuration Items? If applicable, was the baseline updated per the review?; Baseline Audit Plan & Report Baseline Package. Configuration Management; Task; Were required inputs to 'Perform Change Management' provided to the Project Team?; Change Request/Problem Report Configuration Control Standard Impact Assessment Standard. Configuration Management; Task; Are change control procedures in place for the project (from the beginning) which initiate, record, review, approve, and track change requests and problem reports?; Change Control Procedures Change Request/Problem Report. Configuration Management; Task; Were the required outputs to 'Perform Change Management' created by the Project Team?; Change Request/Problem Report. Configuration Management; Work Product; Does the Change Request/Problem Report meet the Standards? (Note: Both the Configuration Control Standard and the Impact Assessment Standard need to be checked.); Change Request/Problem Report. Configuration Management; Step; Does the Information System Security Office (ISSO) approve CR's/PR's that involve security requirements?; Change Request/Problem Report. | January 13, 2016 | 7 hrs | Karen Black Tim Queen |
| APL Governance Audit #3 Discipline; Process component; Question or data evaluated; Generic target artifact. Development; Task; Were required inputs to 'Design the Solution' provided to project?; Design Standard Traceability Matrix [Technical Architecture] [Technical Specification]. Development; Task; Have the elements been identified along with their interactions, behavior, relations, and data necessary to realize some functionality?; Design. Development; Task; Were the required outputs to 'Design the Solution' created by the project?; Design Traceability Matrix. Development; Work Product; Does the Design meet the Standard?; Design. Development; Task; Were required inputs to 'Create Developer Tests' provided to the developer?; Traceability Matrix [Software Implementation]. Development; Task; Were developer tests implemented to validate individual implementation elements?; Developer Test. Development; Task; Were the required outputs to 'Create Developer Tests' created by the project?; Developer Test Traceability Matrix. Development; Task; Were required inputs to 'Develop Solution' provided to the developer?; Traceability Matrix [Software Design] [Technical Specification] Coding Standards. Development; Task; Was new or modified code created as part of the solution or to fix a defect?; Implementation (code). Development; Task; Were the required outputs to 'Develop Solution' created by the project?; Implementation (code) Traceability Matrix. Development; Work Product; Does the code meet the standard?; Coding Standards. Development; Task; Were required inputs to 'Run Developer Tests' provided to the developer?; Developer Test [Software Implementation]. Development; Task; Were developer tests executed to validate individual implementation elements?; Test Log. Development; Task; Were the required outputs to 'Run Developer Tests' created by the project?; Test Log. Development; Task; Were required inputs to 'Integrate and Create Build' provided to the developer?; Developer Test [Software Implementation]. Development; Task; Were integration tests performed on the integrated code base for build validation?; Build Procedures Build Integration Tests. Development; Task; Were the required outputs to 'Integrate and Create Build' created by the project?; Build Test Log. Test; Task; Were required inputs to 'Peer Review Selected Work Products' provided to the reviewers?; [Project Work]. Test; Task; Are defects being removed from work products as early in the lifecycle as possible?; Peer Review Results. Test; Task; Were the required outputs to 'Peer Review Selected Work Products' created by the project?; Peer Review Meeting Package (Optional) Peer Review Results. Test; Task; Were required inputs to 'Plan for Formal Peer Reviews (optional)' provided to the Moderator and reviewers?; [Project Work]. Test; Task; Were reviewers selected and roles assigned for the formal peer review?; Review artifacts. Test; Task; Were the required outputs to 'Plan for Formal Peer Reviews (optional)' created by the project?; Peer Review Meeting Package. Test; Task; Were required inputs to 'Conduct Formal Peer Reviews (optional)' provided to the reviewers?; Peer Review Meeting Package [Project Work]. Test; Task; Were defect identified and action items documented?; Peer Review Meeting Package. Test; Task; Were the required outputs to 'Conduct Formal Peer Reviews (optional)' created by the project?; Peer Review Meeting Package. Test; Task; Were required inputs to 'Conduct Formal Peer Reviews (optional)' provided to the reviewers?; Peer Review Meeting Package [Project Work]. Test; Task; Were defect identified and action items documented?; Peer Review Meeting Package. Test; Task; Were the required outputs to 'Conduct Formal Peer Reviews (optional)' created by the project?; Peer Review Meeting Package. Test; Task; Were required inputs to 'Follow-up on Formal Peer Review Results (optional)' provided to the Moderator and Author?; Peer Review Meeting Package [Project Work]. Test; Task; Was rework from defects and action items identified in the peer review meeting resolved and were measurements recorded in the Peer Review Repository on the ISE C&C Portal?; Peer Review Meeting Package [Project Work] Peer Review Results. Test; Task; Were the required outputs to 'Follow-up on Formal Peer Review Results (optional)' created by the project?; Peer Review Results. Test; Task; Were required inputs to 'Create Test Cases' provided to the Tester?; Test Information Standard Test Plan (optional) Traceability Matrix [Technical Specification]. Test; Task; Were test cases and test data for the requirements to be tested developed?; Test Information. Test; Task; Were the required outputs to 'Create Test Cases' created by the project?; Test Information Test Plan (optional) Traceability Matrix. Test; Work Product; Does the Test Information meet the Standard?; Test Information. Test; Task; Were required inputs to 'Implement Tests (optional)' provided to the Tester?; Test Information Test Information Standard Test Plan (optional). Test; Task; Were test scripts implemented to validate a build of the solution?; Test Information Test Information Standard Test Plan (optional). Test; Task; Were the required outputs to 'Implement Tests (optional)' created by the project?; Test Information Test Information Standard Test Plan (optional). Test; Work Product; Does the Test Information meet the Standard? (Note: This WP might have been checked against the Standard already.); Test Information. Test; Task; Were required inputs to 'Customer Acceptance Testing' provided to the Tester?; Test Plan (optional). Test; Task; Was the system verified that it works accoring to requirements and did the customer officially accept the system?; Test Information Test Plan (optional). Test; Task; Were the required outputs to 'Customer Acceptance Testing' created by the tester?; Test Information Test Plan (optional). Security; All. Supplier Agreement Management; All. | March 16, 2016 | 7 hrs | Karen Black Tim Queen |
| Baseline Audit | Nov 14 | 4 hours | Karen Black |

# Software Configuration Management Plan

The Configuration Management (CM) activities performed to manage the configuration of the CCO eCoaching Log are specified in the GDIT Health Solutions SCM plan and the CCO SCM Charter.

A copy of the HS SCMP plan can be found at http://hq100-rtnlweb:8080/apl/aim_build.practice.mgmt.team_change_mgmt.base/guidances/examples/resources/HS_SCMP.docx

A copy of the charter can be found in TFS named  Charter\CMS_Project_SCCBCht.doc

Documents will be named one of two ways depending on the nature of the document.  Documents that are specific to an option period, such as this document,  will be named CCO OYx eCoaching Log[document name] where x represents the option year number.  Documents that are not specific to an option period, such as the FS will follow the convention of CCO eCoaching Log [document name]. Documents that do not currently meet that specification will be renamed when they are worked on as part of Work Item.  New documents that are created will follow the appropriate naming convention.

# Lifecycle Selection

The Lifecycle selection process has been completed with a suggested lifecycle of APL Build Maintenance.  A screen shot of the selection process is below.