## Sheet1
Performance Management Lessons Learned
Title | Date | Name | Role | Lesson Description | Recommended Action | Project Phase
Capture of Lessons Learned | 2014-06-30 | Tim Queen | SPM | Not having a central location for housing project lessons learned makes it impossible to accurately and completely retrieve them later. The purpose of retrieving the lessons learned data is to analyze, learn, share, and improve the way we perform our work. | 1. Create a List on the team site to capture all project lessons learned. 2. Add the topic of Lessons Learned to the weekly team meeting agenda. 3. Document lessons learned as identified during team meetings, monthly iteration assessments, and at the end of unique initiatives or projects. 4. Perform a quarterly analysis of lessons learned and share with the team. | Inception