## Velocity Size Defs
Relative Size Definition/Ranges Table (ORIGINAL)
| Relative Size Value | Relative Size Description | Range
| 1 | Very Small | <=2 hours
| 2 | Small | >2 hours <=8 hours
| 3 | Medium | >8 hours <= 16 hours
| 4 | Large | >16 hours <=40 hours
| 5 | Large x2 | >40 hours <80 hours
| 6 | Large x3 | >80 hours <120 hours
| 7 | Large x4 | >120 hours <160 hours
| 8 | Large x5 | >160 hours <200 hours
| 9 | Large x6 | >200 hours <240 hours
| 10 | Large x7 | >240 hours <280 hours
| 11 | Large x8 | >280 hours <320 hours
| 12 | Large x9 | >32 hours <360 hours
| 13 | Large x10 | >360 hours <400 hours

## M12-May
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M12 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M12 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M12 | Jourdain
SCRs Submitted
Misc Current
Security

## M11-April
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M11 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M11 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M11 | Jourdain
SCRs Submitted
Misc Current
Security

## M10-March
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M10 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M10 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M10 | Jourdain
SCRs Submitted
Misc Current
Security

## M9-Feb
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M9 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M9 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M9 | Jourdain
Migration to AD
Escalated Issues
Production Support
SCRs Submitted
Misc Current
Security

## M8-Jan
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M8 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M8 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M8 | Jourdain
Migration to AD
Escalated Issues
Production Support
SCRs Submitted
Misc Current
Security

## M7-Dec
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M7 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 |  | M7 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 |  | M7 | Jourdain | 2 | 1 | 2
SCRs Submitted
Misc Current
Security

## M6-Nov
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M6 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 |  | M6 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 |  | M6 | Jourdain | 2 | 1 | 2
SCRs Submitted
Security

## M5-Oct
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M5 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 |  | M5 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 |  | M5 | Jourdain | 2 | 1 | 2
SCRs Submitted
Misc Current
Security

## M4-Sept
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M4 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 |  | M4 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 |  | M4 | Jourdain | 2 | 1 | 2
SCRs Submitted
Misc Current
Security

## M3-Aug
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M3 | Suzy/Jourdain | 1 | 2 | 1.7
Monthly Password Updates |  | H | 1 |  | M3 | Suzy/Jourdain | 1 | 1 | 1
Database Service Account Update |  | H | 1 |  | M3 | Jourdain | 2 | 1 | 1.2
SCRs Submitted
Misc Current
Security

## M2-July
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M1 | Suzy/Jourdain | 1 | 2 | 1.5
Monthly Password Updates |  | H | 1 |  | M1 | Suzy/Jourdain | 1 | 1 | 1.5
Database Service Account Update |  | H | 1 |  | M1 | Jourdain | 2 | 1 | 1.5
SCRs Submitted
Misc Current
Security

## M1-June
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 | Open | M1 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 | Open | M1 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 | Open | M1 | Jourdain | 2 | 1 | 2
SCRs Submitted
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1
Phase II Work/Deliverables
User Stories | 1 | M |  | Open | I1 | Doug Stearns
Use Cases | 2 | M |  | Open | I1 | Doug Stearns
E1 Iteration Plan | 3 | M |  | Open |  | Tim Queen
Misc Current
Security