## Sheet1
eCoaching Log Lessons Learned
Title | Date | Name | Role | Lesson Description | Recommended Action | Project Phase
Capture of Lessons Learned | 2014-06-30 | Tim Queen | SPM | Not having a central location for housing project lessons learned makes it impossible to accurately and completely retrieve them later. The purpose of retrieving the lessons learned data is to analyze, learn, share, and improve the way we perform our work. | 1. Create a List on the team site to capture all project lessons learned. 2. Add the topic of Lessons Learned to the weekly team meeting agenda. 3. Document lessons learned as identified during team meetings, monthly iteration assessments, and at the end of unique initiatives or projects. 4. Perform a quarterly analysis of lessons learned and share with the team. | Inception
Regression testing should be performed when major changes are made | 2015-05-14 | Tim Queen | SPM | Changes made to one part of the system may have a negative impact on other parts of the system | Create regression test cases that can be used when significant changes are made to eCL. | Maintenance