## Q1
CCO eCoaching Log
Schedule
| Planned milestone finish date |  | 2016-08-31 |  | Q1 iteration completed. June 1 - Aug 31
| Actual/Forcast milestone finish date |  | 2016-08-31
| Milestone % Complete |  | 100%
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
| Critical | 1 | 1 | N/A | N/A
| High | 3 | 3 | N/A | N/A
| Medium | 2 | 2 | N/A | N/A
| Low | 0 | 0 | N/A | N/A
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0! | No peer reviews were performed in this period.
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
| Critical | 3 | 3 | N/A | N/A
| High | 20 | 13 | N/A | N/A
| Medium | 3 | 2 | N/A | N/A
| Low | 5 | 4 | N/A | N/A
Effort
|  | Iteration to date | OYTD |  |  | Analysis
| Bid | 771 | 771 |  |  | Analysis
| Actual | 994 | 994 |  |  | Additional effort required from Suzy and Doug than expected
| Bid Variance | 223 | 223
| Percent | 28.92% | 28.92%
| Size of Work Items | Current Iteration |  | Iteration Objective |  | Analysis
| Small (< 20 hrs) | 26 |  | 8 |  | More smaller admin tasks than estimated.
| Medium (20 - 80 hrs) | 2 |  | 5
| Large (> 120 hrs) | 0 |  | 1
Cost
|  | Iteration to Date | OYTD |  |  | Analysis
| Bid | 72769.6315 | 72769.6315 |  |  | Additional effort required from Suzy and Doug than expected
| Actual | 89322.811 | 89322.811
| variance | 16553.1795 | 16553.1795
| Percent | 22.75% | 22.75%

## Q2
CCO Assignment and Exception Tracking System Measurements
Schedule
| Planned milestone finish date |  | None |  | The A&E system does not currently have any milestone targets.
| Actual/Forcast milestone finish date |  | None
| Milestone % Complete |  | N/A
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
Critical
High
Meduim
Low
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0!
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
| Critical | Open | Closed | Open | Closed
High
Meduim
Low
Effort
|  | Iteration to date | Variance | YTD | Variance | Analysis
Iteration Bid
Iteration Forecast
Iteration Actual

## Q3
CCO Assignment and Exception Tracking System Measurements
Schedule
| Planned milestone finish date |  | None |  | The A&E system does not currently have any milestone targets.
| Actual/Forcast milestone finish date |  | None
| Milestone % Complete |  | N/A
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
Critical
High
Meduim
Low
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0!
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
| Critical | Open | Closed | Open | Closed
High
Meduim
Low
Effort
|  | Iteration to date | Variance | YTD | Variance | Analysis
Iteration Bid
Iteration Forecast
Iteration Actual

## Q4
Q4
Schedule
| Planned milestone finish date |  | None |  | The A&E system does not currently have any milestone targets.
| Actual/Forcast milestone finish date |  | None
| Milestone % Complete |  | N/A
Quality
| Number of defects by severity | Current Iteration |  | Prior Iteration |  | Analysis
|  | Open | Closed | Open | Closed
Critical
High
Meduim
Low
| Peer Reviews | Number of defects | Total Effort | Number of reviewers | Effort per defect found | Analysis
| Functional Spec |  |  |  | #DIV/0!
| Detail Design |  |  |  | #DIV/0!
| Open vs Closed Change Requests | Current Iteration |  | Prior Iteration |  | Analysis
| Critical | Open | Closed | Open | Closed
High
Meduim
Low
Effort
|  | Iteration to date | Variance | YTD | Variance | Analysis
Iteration Bid
Iteration Forecast
Iteration Actual