# Title: CCO eCoaching Log

# Software Project Plan

June 30, 2014

Revised 2/6/2015

Table of Contents

1	Introduction	3

2	Project organization	3

3	Project measurements	4

4	Project milestones and objectives	9

5	Stakeholder plan	11

6	Project Security Plan	16

7	Tools and environment	17

8	Peer Review Work Product Selection and Approach	20

9	Formal Decision Approach	20

10	Project Training Plan	20

11	Deployment	22

12	Lessons learned	23

13	Governance Plan	23

14	Software Configuration Management Plan	24

15	Lifecycle Selection	24

# Introduction

The eCoaching log (eCL) project plan will provide a high-level overview of the project and will serve as the formal document used to execute the requirements of the eCL application and input from the project stakeholders. The project plan will document our approach and methodology used by the eCL Engineering team.

The eCL is designed to provide feedback to CSRs of the Contact Center Operations (CCO), including alternate channels (e.g. Web Chat, ARC, Written Correspondence). The eCoaching Log builds on our goal of continuous improvement to achieve sustainable results.

Supervisors and Managers submit eCLs for a CSR to correct unfavorable behavior. They submit eCLs through a front-end Internet application which gets delivered to the CSRs manager for coaching. Depending on the type of coaching required, both Supervisor and Manager could be required to review and sign-off.

Two feeds exist for the eCL application:

- Outlier data to identify coaching opportunities. This was implemented in April, 2013.  The feed was created to be able to pull in 1 of 14 various outlier data feeds, currently only a few have been sent to eCL.

- IQS feed (via LimeSurvey®)  and Verint.

The eCoaching Log contains a component for CSRs to have the ability to comment on, or simply acknowledge the coaching comments entered by the supervisor or manager. The eCoaching Log establishes consistency and ease of use in our coaching notes process along with providing historical coaching data for all CSRs.

During this option year, several enhancements are planned to provide more functionality to the eCL system.  These enhancements will be done through SCRs if they are minor in nature.  Larger enhancements will be documented in this plan as they arise.

# Project organization

- Tim Queen is the Software Project Manager for the eCoaching Log and works out of the Lawrence office.  He will be creating weekly status reports and holding weekly touch-base meetings with the eCoaching Log Program Leads.

- Susmitha Palacherla is the lead developer and works remote out of her Atlanta, Georgia home office.  Her role will be to support database, ETL and SSAS enhancements.

- Dave Hinman is senior developer who works out of the Coralville, Iowa office.  His role will be to support database, ETL and SSAS enhancements and back-up Suzy.

- Jourdain Augustin is the lead web developer who works out of Fairfax, Virginia.  His role will be to support web development.

- Doug Stearns is a requirements and test engineer who works out of the Coralville, Iowa office.  His role will be to support testing and requirements.

As indicated above, the eCL project interacts with the Interface to Quality Systems (IQS), Verint and the LimeSurvey® scorecard system. These systems provide the results of monitoring of CSR in the CCO.  Dave Hinman is the lead developer on the IQS.

# Project measurements

| Organizational Standard Metrics |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Information Need | Measurement | Resp. Role | Analysis Method | Analysis and Reporting Frequency | Source |  | Where Data and Results are Stored | Who Receives Data |
| Effort/Cost |  |  |  |  |  |  |  |  |  |
| Manage project effort to commitments from the Proposal/BOE. | Compare planned effort with actual effort: • Are we delivering to our plan? • How accurate are our estimates? • Are we delivering to our estimates? • Are certain tasks or activities taking more/less effort than expected? • How much effort will it take to perform project activities? | Actual effort variance to plan effort ((Actual effort – plan effort)/plan effort) * 100 Percentage over or under plan Iteration trends | Project Manager | Understanding how estimates compare to actual results is a key measure of project progress in meeting commitments. Establishing a trigger to alert management and the project team when corrective actions are needed enables project teams to realize the full benefit of this metric. Corrective action should be taken when actual variance to plan effort exceeds a threshold of +/- 10%. | Iteration | Oracle |  | Data is stored in Oracle. Reports and analysis results are stored in location specified in CI/DI list. | Project Manager Program Manager |
| Manage the project to meet or exceed commitments from the Proposal/BOE and sector financials. | To provide insight into planned and or estimated cost compared to expended cost on projects: • How accurate are our estimates? • Are we delivering to our estimate? • Are we delivering to our plan? • How much cost will it take to perform project activities? | Actual cost variance to plan cost ((Actual cost – plan cost)/plan cost) * 100 Percentage over or under plan Iteration trends | Project Manager | Understanding how cost estimates compare to actual results are a key measure of project progress in meeting project commitments and give project and program managers and teams the ability to take corrective actions. Corrective action should be taken when actual variance to plan effort exceeds a threshold of +/- 10%. Analysis and understanding of this data over time will also help to improve the accuracy of future estimates. | Iteration | CostPoint |  | Data is stored in CostPoint. Reports and analysis results are stored on project SharePoint site (furnish url) | Project Manager Program Manager |
| Schedule |  |  |  |  |  |  |
| Provide insight into schedule variation from plan and progress to achieving milestones. | • Deliver on our commitments. • Meet deadlines. • We deliver to our estimates. • Control costs. | Planned milestone finish date Record during project and/or iteration planning | Project Manager | Projects behind schedule typically require some sort of corrective action. Projects ahead of schedule may want to consider releasing committed resources that are no longer needed back to the organization. | Iteration | MS Project |  | Data is stored in MS Project Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Provide insight into schedule variation from plan and progress to achieving milestones. | • Deliver on our commitments. • Meet deadlines. • We deliver to our estimates. • Control costs. | Actual/Forecast milestone finish date Record during project execution | Project Manager |  | Ongoing | MS Project |  | Data is stored in MS Project Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Provide insight into schedule variation from plan and progress to achieving milestones. | • Deliver on our commitments. • Meet deadlines. • We deliver to our estimates. • Control costs. | Milestone % Complete Record during iteration while executing iteration plan | Role or individual responsible for a given milestone |  | Ongoing | MS Project |  | Data is stored in MS Project Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Quality |  |  |  |  |  |  |
| Provide insight into the quality of the system/solution to be delivered. | Are we delivering a quality product? • How many problem reports have been opened? • What are their severities? | Number of defects by severity Count all defects by their severity code Possible representation: Stacked vertical bar graphs illustrate the relative weighting of defect severity types | Project Manager | • Are most of the defects being found critical with severe system impacts, or relatively minor? • Is severity trending upward or downward? • Are there particular areas of the system/software with larger quality issues than others? | As needed and determined by the project | Team Track |  | Data is stored in Team Track Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Provide insight into the quality of the system/solution to be delivered. |  | Open vs. Closed Defects All SCRs of type Problem Report and Status = Open compared to all SCRs of type Problem Report and Status = Closed Possible representation: Trend graph over time (e.g., by iteration) | Project Manager | Are defects being opened faster than they are being closed? • Are we opening more or fewer defects this iteration than last? Answers to these questions are good indicators for project managers and team members of how the project’s quality profile is progressing. | As needed and determined by the project | Team Track |  | Data is stored in Team Track Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |
| Evaluate the effectiveness of defect detection through the project lifecycle. | How effective are peer reviews at removing defects? • How much time is spent on peer reviews? • How many defects per effort hours are discovered during peer reviews? • What types of work products undergo peer review? • Are we delivering a quality product? | Peer Reviews Project Name Work Product Type - Architecture - Design - Code - Project Management - Requirements - Testing - Other (specify your own value) Phase/Iteration ID Number of Defects Total effort (hours) Number of reviewers Effort per defect found = (Total hours / Number of Defects) | Project Manager | Analyze the project's defect discovery rate (I.e., Effort per defect found) and determine if the rate meets the projects needs and expectations. | As needed and determined by the project | http://cwe.vangent.local/sites/AIMWiki/AIM_Support/Lists/Peer%20Review%20Measurements/Peer%20Review%20Defect%20Analysis.aspx |  | http://cwe.vangent.local/sites/AIMWiki/AIM_Support/Lists/Peer%20Review%20Measurements/Peer%20Review%20Defect%20Analysis.aspx | Project Manager |
| Provide insight into requirements stability | • How many change requests have been opened? • How many change requests are currently open? | Open vs. Closed Change Requests All SCRs of type Change Request and Status = Open compared to all SCRs of type Change Request and Status = Closed | Project Manager | • Are change requests being opened faster than they are being closed? • Are we opening more or fewer change requests this iteration than last? Answers to these questions are good indicators for project managers and team members of how stable project requirements are. Requirements are typically not stable initially as the team collaborates with customers and other stakeholders to derive customer requirements. However, requirements that are continually changing too far into the SDLC may impact milestone dates and product quality. | As needed and determined by the project | Team Track |  | Data is stored in Team Track Reports and analysis results are stored in location specified in CI/DI list. | Project Manager |

| Project Specific Metrics |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Information Need | Measurement | Resp. Role | Analysis Method | Analysis and Reporting Frequency | Source | Where Data and Results are Stored | Who Receives Data |
| None |  |  |  |  |  |  |  |  |

The Bid vs Actual hours can be found at:

http://extranet.vangent.local/PublicHealthCareTeamSites/CMSExtranet/Performance%20Management%20Team%20Site/ScorecardAppDevelopment/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FPublicHealthCareTeamSites%2FCMSExtranet%2FPerformance%20Management%20Team%20Site%2FScorecardAppDevelopment%2FShared%20Documents%2FEngineering%20Planning%2FCCO%20OY1

The Performance Scorecard and the eCoaching Log systems are bid as one under the CCO contract.  They use the same charge code and share resources.

# Project milestones and objectives

Project Milestones and objectives will be tracked in the project management schedule, WBS and work items list. The Microsoft Project schedule is located here:

- http://vmsps2010app01/PWA/Project%20Detail%20Pages/Schedule.aspx?ProjUid=f8e8a3cb-de6f-4c48-b74a-dfc1dd2f9efa

All minor changes related to the system will be identified and worked with the Software Change Request process. This may include but is not restricted to security changes, new reports, new data feeds, database and user interface updates.

| Iteration | Primary objectives (risks and use case scenarios) | Scheduled start or milestone | Target velocity |
| --- | --- | --- | --- |
| M | Maintenance Iterations M1-M12 Objectives: - Planned SCRs - Close-out Process and Policy (Active/Inactive) - Integration of eCL Dashboard with CSR Performance Scorecard - Administrative Backend - Security and system patching - Issue Log research and resolution | 6/1/2014 – 5/31/2015 | 15 |

Major changes to the eCL are planned for OY2.  These changes will be managed as a project.  Some of the changes will go through multiple iterations while others may be a single iteration.

Modular Coaching

| Iteration | Primary objectives (risks and use case scenarios) | Scheduled start or milestone |
| --- | --- | --- |
| I1 | - Define the major components of Phase 2 - Modular Coaching Platform - Supervisor ¦ Quality - Create Vision & user stories - Achieve concurrence - Create use cases / requirements - Identify changes to the existing Architecture | 6/1/2014 – 7/15/2014 |
| E1 | - Validate the architecture - Refine requirements - Develop prototype of KPA section of eCL that is modular driven - Prototype home page driving coaching page | 7/10 – 7/18 |
| C1 | - Refine requirements - Finalize Home page changes - Finalize KPA approach for asking questions and capturing responses - Create supervisor eCL functionality using a modular driven approach | 7/12 – 8/29 |
| T2 | - Implement new home page and additional group | 8/29 |
| T3 | - Implement additional group (Quality) | 9/30 |
| T4 | - Implement additional group (Training) | 3/15 |
| T5 | - Implement additional group (LSA) | 1/30/15 |

Dashboard Functionality

| Iteration | Primary objectives (risks and use case scenarios) | Scheduled start or milestone |
| --- | --- | --- |
| I1 | - Define the major components of Phase 3 - Dashboard redesign - HR access - Develop low CSAT feed o Training Module - Inactivation / re-assignment admin tool - Reporting - Add new pending statuses to Dashboards - Prevent users from submitting eCL for themselves Start 2/9 - Outliers to use isCSE set to 1 o Security data feed - Revise text layout of description field in review forms - Open comment fields on all review forms - Include “value” in dashboard o Counts of opportunities / reinforcements to account for met goal / did not meet goal - Create Vision & user stories - Achieve concurrence - Create use cases / requirements - Identify changes to the existing Architecture | Start 2/9 |
| E1 | - Validate the architecture - Refine requirements - Prototype page layout - Prototype database queries to return data required for display - Prototype graphics |  |
| C1 | - Refine requirements - Complete graphics |  |
| C2 | - Refine requirements - Develop remaining components of dashboard |  |
| T1 | - Implement new dashboard |  |

# Stakeholder plan

| Role | Assigned Person(s) | Communications Plan | Responsibilities |
| --- | --- | --- | --- |
| *Customer | Scott Mainwaring, Program Vice President Lori Lindstrom, Program Vice President Evan Davis, Director Business Process Improvement and Analytics Scott Reynolds, Program Manager Analytics and Reporting Brian Dye, Quality Director Steven Schreiber, Alternate Channels Director JP Chalarca, ARC Program Manager Rick Graybill, Email/Chat Program Manager | email Teleconferences Status Reports TeamTrack | Provide requirements for the CCO program |
| *Program Manager | Brian Dye John Tiongson | email Face-to-Face Meetings Teleconferences TeamTrack Weekly project calls | Provide requirements for the CCO program Responsible for the planning, monitoring and controlling the program to ensure that it meets with its business plan goals, and for reporting performance against plan. Serves as communication liaison between the customers, project staff and the development staff. |
| *Tester | Doug Stearns | Email Teleconferences TeamTrack Standup meetings Meetings with SPM | Leads the creation of the Functional Specification and Traceability Matrices Focal point of communication with the customer on issues that arise in the system. Leads the creation of the System Test Plans and Test Cases. Coordinates and participates in the execution of the System Test Plan and cases. For work done within TeamTrack, responsible for the effort, estimate, and testing is all encompassing for the issues being corrected. |
| *SCM Lead | Jackie Miller | Email Teleconferences TeamTrack | Leads all SCM activity. Creates and maintains the SCCB charter. The SCM lead is a member of the SCCB. Facilitates the SCCB meetings Generates the SCCB meeting minutes Provides SCM tool training and support |
| *Project Manager | Tim Queen | Email Teleconferences TeamTrack Daily standup meetings Weekly meetings with the program 1 to 1 with direct reports Meeting with MGR MBR Presentation Document Reviews SharePoint | Develops and updates the project plan Ensures the software development is completed on time and within budget, and serves as contact between project staff and development resources. Responsible for Risk Management and Measurement and Analysis including monthly reporting to senior management and program manager. Responsible for production status and issues Responsible for directing development resources to ensure a quality product from development to production support. Responsible for coordinating the effort between development, testing and business analysts Responsible for formal decision making (DAR) Responsible for project measurement (MA) |
| *Process Auditor | Karen Black | eMail Governance Monthly Report Governance audit plans and reports SharePoint TeamTrack Version Manager | Objectively evaluating performed processes, work products, and services against the applicable process descriptions, standards, and procedures Identifying and documenting noncompliance issues Providing feedback to project staff and managers on the results of quality assurance activities Ensuring that noncompliance issues are addressed Mentoring projects on process usage |
| *Risk Management | *All project members | Team meetings Weekly team status meetings Document Reviews SharePoint TeamTrack Version Manager eMail | Participates in monthly risk management review Identifies risks as needed |
| *Validation | eCoaching Log Team | Team meetings Weekly meetings with customer Document reviews SharePoint TeamTrack Version Manager email | SPM assures that all validation activities are carried out. All team members have the responsibility to identify and report any validation issues. |
| *Project Security Analyst | Brian Szabo | Email Teleconferences TeamTrack | Performs monthly and quarterly scans to ensure compliance. Mentors team on security awareness. Participates in SCCB meetings to provide security oversight and approval. |
| *Developers | Dave Hinman Jourdain Augustin Susmitha Palacherla | email Face-to-Face Meetings Teleconferences TeamTrack Team meetings Bi-Weekly 1 to 1 with SPM | Software development and unit testing Documentation updates Support production operations. |
| *Development Team Lead | Susmitha Palacherla | email Face-to-Face Meetings Teleconferences TeamTrack Bi-Weekly 1 to 1 with SPM | Leads the design effort for the project Leads the coding and unit testing of applications Will be involved in the creation of baselines as well as the baseline audit Responsible for the coordination of development efforts Coordinates the system test and production builds |
| * Stakeholders | Supervisors CSRs Contact Center Managers CCO Program Management Senior Management | email Face-to-Face Meetings Teleconferences TeamTrack | Provide requirements for the CCO program Identify any issues with the application |
| Senior Management | Jacquie Haltmeyer John Hess | MBR Presentations Weekly status report Bi-Weekly 1 to 1 with manager SharePoint TeamTrack Schedule eMail | Responsible for assisting the Program Manager and software project manager with planning, monitoring, and controlling the program to ensure that it meets its business plan goals, and for reporting performance against the plan. Serves as communication liaison between the customers, project staff, and development staff. Breaks down barriers for the team. Helps provide necessary resources while balancing the needs of the CCO program against the business unit. Used as a mentor to help guide the software project manager. |
| Data Feed Providers - High Point Global - LimeSurvey | SPM – Tim Queen | eMail TeamTrack Teleconferences | Participate in meetings with the team. Provide feedback on requirements. Provide feedback during testing. Coordinate changes in data feed consumer systems that impact team. |

*Required Roles

# Project Security Plan

This is a Vangent initiated application not located on the 10.43 network and does not store or retain any PHI data. Thus the eCoaching Log application falls under GDIT security policies and will not fall under the systems audited by Mitre.

The eCoaching Log servers were requested to be built based on the Vangent Windows Server Standard Build, and will follow this standard install for all rebuilds.  This document can be found in Version Manager.

\\cmlibrary_02\cms\archives\Global Documentation\Security\Server Standard Build\ Windows Server Build Standards - GOLD - v5 1

The project is requesting a waiver for the creation of the following security documents:

* Application Threat Modeling

* Application Security Risk & Requirements

* Acceptable Risks and Safeguards Audit

and from performing

* Evaluate code for security

* Evaluate security testing

* Review test activities for security

* Verify operations security

This waiver request is to be approved by the program manager. Acceptance of the plan by the program manager will suffice as acceptance of the waiver request.

# Tools and environment

# System Environment

| Process Area | Methodology Standard Used |
| --- | --- |
| Code – SQL Server | Microsoft SQL Server Books Online |
| Code – ETL | The Data Warehouse Toolkit by Kimball and Ross, Wiley Publishing; 2002 The Microsoft Data Warehouse Toolkit by Mundy, Thornthwaite and Kimball, Wiley Publishing; 2006 |
| Code – MDX | MDX Solutions, Second Edition by Spofford, et. al; Wiley Publishing; 2006 |

Development, Test, and Production Environment Software

| Software Requirement | Description |
| --- | --- |
| Computer Resource Requirements | Below are the common software tools used by software projects. Process Section; Tool; Description. Project Management; Microsoft Project 2010; Schedule Management. Team Track 6.6.1.19; Automates Configuration Control. Requirements; Microsoft Word 2010; Create Text. Microsoft Excel 2010; Creates Spreadsheets. Microsoft Visio 2010; Creates Graphics. Team Track 6.6.1.19; Automates Configuration Control. Design; Microsoft Word 2010; Create Text. Microsoft Excel 2010; Creates Spreadsheets. Microsoft Visio 2010; Creates Graphics. Architecture; Microsoft Word 2010; Create Text. Microsoft Excel 2010; Creates Spreadsheets. Microsoft Visio 2010; Creates Graphics. Code Other (SQL dev license)- E32-00693-2- Todd (sql Dev License) - MC46H-JQR3C-2JRHY- XYRKY-QWPVM; Visual Studio 2008 SQL Server 2008Express SQL Server Manager Studio 2005 Express Log Parser 2.2 Visual Web Developer 2010 Express SQL Server 2008 Express Toolkit Windows Script Host 5.8; Source Code Editor. Unit/Integration/System Testing; SQL Server 2008 Visual Studio 2008 Shell Beyond Compare 3 Snag it 8.2; Testing Tools. Implementation. SFTP 5.1; Communication. Software Configuration Management / Data Management; Version Manager 8.3; Version Manager. Team Track 6.6; Version Manager. SharePoint 2010; Data management version control. Applications; Server Installed; License. SQL DB; VRIVFSSDBT02 VDENSSDBP07; Standard. |
| Network Availability Requirements | This project requires no specific network availability considerations beyond the standard network availability provided by the organization. |
| Shared Computer Resources | The project uses virtual database servers for the development and testing environments which are shared environments. |

Computing System Environment

The environments consist of the developers PCs, a virtual web server and virtual database server.  All developers and testers have access to the tools described above.  The following section describes the hardware used in each of the environments.

# Development, Test, and Production Environment Hardware

| Hardware Requirement | Description |
| --- | --- |
| Computer Resources - Production Environment | VDENSSDBP07\SCORP01,1436 – Virtual Database Server owned by the program used for all data storage, retention and transformation of feeds and load data. VADENMWBP11 – Virtual web server owned by the program used for the web front end |
| Computer Resources – Development and Integration Environment | VACMSMPMD01 – Virtual web server owned by the program used to host the web front end for development. |
| Computer Resources – Testing Environment | VACMSMPMD01 – Virtual web server owned by the program used to host the web front end for testing. |
| Network Availability |  |
| Shared | VRIVFSSDBT02\SCORD01, 1437 – Virtual database server owned by GDIT used for development VRIVFSSDBT02\SCORT01, 1438 – Virtual Database server owned by GDIT used for testing VRIVSCORS01 –Virtual staging server owned by GDIT used to stage and archive source files. |

# Facilities Planning

| Facilities Requirement | Description |
| --- | --- |
| Development | There are no specific facility requirements. |
| Test – Internal | There are no specific facility requirements. |
| Test – Customer Acceptance | There are no specific facility requirements. |
| Production | There are no specific facility requirements. |

# Peer Review Work Product Selection and Approach

The project will perform a peer review of the following items:

- Requirements Document

- Design Document including database structure

- Code

The rationale behind doing peer reviews for these components is they have high visibility within the program and are critical to CCO operations.  Peer reviews will be done be members of the development team.

Informal peer reviews will be performed by the team.

Peer reviews will be performed at the completion of each Construction iteration and at the end of each Transition Iteration.

# Formal Decision Approach

The project will follow the Decision Analysis and Resolution process to make formal decisions. Meetings will be established for any DAR activity.  The DAR log will be completed and stored on the project SharePoint site.

When any of the following criteria are met, this project follows the DAR process.

- Mitigation and contingency planning for a complex risk that has a risk exposure of medium or higher.  Complexity is determined by consensus.

- Decisions which require documentation.

- Solution determination which impacts the project cost by +/-10%.

- Solution determination which negatively impacts the schedule of a critical deliverable.

- Solution determination which impacts Operations performance or SLAs.

# Project Training Plan

GDIT and CCO Annual Required Training

All GDIT/Vangent employees are required to complete annual Vangent Security Awareness and Ethics and Compliance Training available through myLMS. CCO Communications alerts staff to all required training.

CCO Project Training

GDIT/Vangent retains a wide and diverse group of technical professionals to staff its projects.  Any organizational or specific training and gap analysis is identified and tracked via the Organizational Detailed Training Plan.

Team members working within the identified discipline will require the skills identified below.

| Discipline | Skill | Training Required? | Action to acquire |
| --- | --- | --- | --- |
| General Team Skills | Configuration Management tools (Version Management and defect tracking) | No |  |
|  | Product domain orientation | No |  |
|  | Risk Management | No |  |
|  | Agile Process Library (APL) | No |  |
|  | Risk Management | No |  |
| Requirements | Project’s requirements elicitation, definition and analysis approach | No |  |
|  | Requirements modeling and specification development | No |  |
|  | Understanding of requirements management and tracking | No |  |
|  | Using requirements tools | No |  |
|  | Validation | No |  |
| Architecture\ Development | Java development | No |  |
|  | C# development | No |  |
|  | Software Design | No |  |
|  | System Architecture | No |  |
|  | Integration | No |  |
|  | Unit Testing | No |  |
|  | Secure Coding practices | No |  |
|  | 508 Compliance | No |  |
|  | Defect Tracking and Version Management tools (e.g., Version Manger, Subversion, Perforce, Team Track) | No |  |
| Testing (unit, integration and system) | Using testing tools (list tools as applicable) | No |  |
|  | Creation of test plans, cases, procedures, and scripts | No |  |
|  | Familiarity with <x> testing methodology, test case creation and test case execution | No |  |
| Configuration Management | Planning and documenting an appropriate CM process based on project needs | No |  |
|  | Creation of baselines | No |  |
|  | Release Management | No |  |
|  | In-depth knowledge of configuration management and change tracking tools | No |  |
|  | Leading a configuration control group in all CM activities | No |  |
| Project Management | Solicit, compile, and process estimates for all project development activities | No |  |
|  | Create and manage a software project plan | No |  |
|  | Project Management growth training | Yes | PMI training on GDIT myLMS |
|  | Plan, manage, and report measurement data for project | No |  |
|  | Lead project activities to ensure project is delivered as planned | No |  |
|  | Formal decision making (included in APL) | No |  |
| Team Kanban Process | Kanban for Team’s daily work item coordination and communication | Yes | On the job training using a tailored Kanban swim lane diagram |

# Deployment

## Maintenance

Once a software configuration change request (SCR) is approved for impact assessment, the SPM assigns the record to the Requirements and Test engineer and developer for their individual assessments.

An SCR is initially deployed in the development environment.  Following successful unit and development testing, the change is promoted into the system test environment by an individual other than the developer.  The promoter role is called the implementer.  The implementer follows the instructions provided by the developer for promotion and implementation.

A successful system test performed by the Test Engineer then routes the change request to be approved for release to the production environment.  Once the SCCB approves to release the SCR to production, the implementer follows implementation instructions to promote to production.

A post-production implementation review is conducted to ensure the software is functioning as expected in the production environment.  This is done by the Test Engineer and a user of the scorecard system.

Configuration items implemented into production are base lined in Version Manager.

## New Development

Occasionally, software will be developed that will be managed as a project activity and not under a SCR. The work will be initially performed in the development environment. Upon completion of the development, the software will be moved to the test environment. A successful test will result in User Acceptance Testing where the end users will perform testing. The system will be deployed to production upon user approval following implementation instructions.

# Lessons learned

Lessons Learned are added and updated as the project progresses.  The Lessons Learned document can be found on the team site at

http://cwe.vangent.local/sites/teams/CMS/Initiatives/eCoachingLog/Planning%20Documents/Forms/AllItems.aspx?RootFolder=%2Fsites%2Fteams%2FCMS%2FInitiatives%2FeCoachingLog%2FPlanning%20Documents%2FLessons%20Learned&FolderCTID=0x01200010FE7D6F0B8AB54A89ECDD6A285B3A12&View={F9DFDD84-A8FB-44A3-975F-AC12E55963C2}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence

The CI/DI List can be found at

http://cwe.vangent.local/sites/teams/CMS/Initiatives/eCoachingLog/Planning%20Documents/Forms/AllItems.aspx?InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence

# Governance Plan

The Software Governance activities for this maintenance project are based on the Agile Process Library (APL) process. The resources and dates are identified below.  Minimal SCRs are planned as the work is being tracked under this project and releases will be in phases.

| Audit | Planned Date | Planned Effort | Resources |
| --- | --- | --- | --- |
| Project Plan Review(s) | May 23 – June 10 | 11 hours | Karen Black Jacquie Haltmeyer John Tiongson |
| APL Process Audit | Nov 10 | 21 hours | Karen Black |
| Baseline Audit | October 1 | 4 hours | Karen Black |

The GDIT HCSD Governance Plan can be found at this location. https://spspi.gdit.com/opshcsd/HCSDOPS/HCSDQA/SQA/Shared%20Documents/Forms/Governance%20Plans.aspx

# Software Configuration Management Plan

The Configuration Management (CM) activities performed to manage the configuration of the CCO Performance Scorecard are specified in the Vangent Health Solutions SCM plan and the CCO SCM Charter.

# Lifecycle Selection

The Lifecycle selection process has been completed with a suggested lifecycle of APL Build Maintenance.  A screen shot of the selection process is below.