## Integrated Register
Integrated Risk Register
Program:
Status | Program | Risk Description | Date Identified | Date Modified | Context | Risk Owner | Origin | Stakeholders | Category | Probability of Occurrence (%) | Impact Rating (1-5) | Total Impact on occurance $ | Risk Exposure Ranking (1 - 25) | Risk Exposure Estimate ($) | Basis of Risk Exposure Estimate | Mitigation Plan | Mitigation Start Date | Mitigation Stop Date | Contingency Plan | Threshold/ Trigger | Contingency Start Date
closed |  | SharePoint site could go down making it impossible to enter data | 2011-06-27 | 2015-02-25 | Occasionally SharePoint is intentionally shut down to fix issues. Additionally, there are sometimes unplanned outages | Tiongson, John | Team | CCO Operations, eCL Engineering | System | 100% | 5 |  | 25 | #VALUE! |  | For administrators, know who to contact to determine status. Have an email form that can fill out to request expedited Help Desk assistance. Communicate expectations. | 2014-04-02 |  | Provide a link to the form and dashboards. Wait and enter the data when SharePoint is restored. Work with IT as needed.SCR 12495 has been opened to move this off SharePoint | SharePoint Outage
Closed |  | If they don't report data accurately, it won't get to the correct supervisor for review. | 2012-04-14 |  | The wrong information is entered and date is not reported to the appropriate people in a timely fashion | Tiongson, John | Team | CCO Operations, eCL Engineering | Operations | 100% | 1 |  | 5 | #VALUE! |  | Provide training for users. Ensure that the message is reinforced through coaching. Provide SOPs for users |  |  | None | Risk is closed
open |  | Incomplete and inaccurate data in centralized CCO CSR/Employee database (eWFM/roster raw) - creates inconsistencies in records being created from external sources (quality control system) compared to records created directly in eCL. | 2012-07-18 |  | Incomplete and inaccurate data in centrallized CCO CSR/Employee database | Tiongson, John | Team | CCO Operations, eCL Engineering | Operations | 100% | 1 |  | 5 | #VALUE! |  | Revised data file sources are being created to reduce this risk along with reporting to identify any issues with the feeds | 2014-04-02 |  | User feed audit report has been created and is being reviewed on a daily basis. | User reports inaccurate data in the eCL
Closed |  | Changes, such as changes to quality monitoring tools may impact functionality and require engineering changes | 2013-05-20 | 2015-02-23 | Utilizing LimeSurvey and Verint; new scorecard and scoring system | Tiongson, John | Team | CCO Operations, eCL Engineering | System | 100% | 5 |  | 25 | #VALUE! |  | None - System will need to be modified to accommodate changes | 2014-05-01 |  | System will be updated as needed | Monitoring system changes; Verint went into production July 1, 2014; closed 2/23/15
closed |  | Notes section for Coaching not required is not always completed and therefore is not providing valuable information for trending | 2013-06-13 | 2015-02-25 | incomplete data in eCL | Tiongson, John | Team | CCO Operations, eCL Engineering | Operations | 100% | 2 |  | 10 | #VALUE! |  | Make this field required | 2014-06-01 |  | Users will be asked to be sure to enter data. Field will be made required | Field is blank
Closed |  | Risk to eCL system performance due to the redesign of the interface and database. Suring submit and review stages. With redesign, looking up many more values. We have one table now, will be sending data to multiple tables and looking up data from multiple tables | 2013-12-11 | 2014-07-30 | Redesign of interface and database could impact eCL system performance | Tiongson, John | Team | CCO Operations, eCL Engineering | System | 25% | 4 |  | 5 | #VALUE! |  | Adequately the the system under load. | 2014-06-13 | 2014-07-30 | Opportunities for improvement will be investigated; hardware changes may be needed | Users are not able to perform their job Risk is Closed 7/30/14
Closed |  | Lack of hierarchy information in data feed for supervisors, managers, sr managers will prevent the proper escalation of eCL issues for Supervisors | 2014-07-17 | 2015-02-23 | Lack of hierarchy information - supervisor--> manager--> sr. manager in peoplesoft feed |  | Suzy | CCO Operations | Operations | 75% | 5 |  | 18.75 | #VALUE! | [5 empty] | Closed 2/23/15 - hierarchy information is in the peoplesoft file
open |  | Engineers supporting multiple projects will have negative impact on delivery of eCL changes | 2014-07-30 | 2015-03-25 | Resources are supporting eCL, Performance Scorecard, A&E, IQS | Tim | Tim | eCL team | System | 85% | 5 |  | 21.25 | #VALUE! |  | Balance work load across engineers to the greatest extent possible to prevent distractions. | 2014-07-30 |  | individuals identified in OY3 will be more aligned with the project
Closed |  | access to warning information | 2015-02-25 | 2015-05-13 | Access to warnings must be limited to specific individuals | John | Team | eCL team | System | 20% | 3 |  | 3 | #VALUE! |  | Access is controlled through an access control list, supervisors and managers | 2015-03-01 |  | Ensure all staff on the project understand the sensitivity of the data | Exposure
closed |  | SMTP server may not working for production | 2015-05-13 | 2015-08-26 | Notifications will not get sent out. | Tim | Team | eCL team | System | 10% | 2 |  | 1 | #VALUE!
Open |  | File share access changing without warning | 2015-05-13 |  | Application will not work | Tim | Jourdain | eCL team | System | 10% | 2 |  | 1 | #VALUE!
open |  | Coaching logs are being entered with PII | 2015-05-13 | [9 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!
[13 empty] | #VALUE! | #VALUE!

## Review History
2015-02-25 | added risk on warnings
2015-03-25 | Updated mitigation on warnings
2015-04-02 | Review of risks with Team no updates
2015-05-13 | Closed row 12; added two new risks