## Velocity Size Defs
Relative Size Definition/Ranges Table (ORIGINAL)
| Relative Size Value | Relative Size Description | Range
| 1 | Very Small | <=2 hours
| 2 | Small | >2 hours <=8 hours
| 3 | Medium | >8 hours <= 16 hours
| 4 | Large | >16 hours <=40 hours
| 5 | Large x2 | >40 hours <80 hours
| 6 | Large x3 | >80 hours <120 hours
| 7 | Large x4 | >120 hours <160 hours
| 8 | Large x5 | >160 hours <200 hours
| 9 | Large x6 | >200 hours <240 hours
| 10 | Large x7 | >240 hours <280 hours
| 11 | Large x8 | >280 hours <320 hours
| 12 | Large x9 | >32 hours <360 hours
| 13 | Large x10 | >360 hours <400 hours

## M1-June
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 | Open | M1 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 | Open | M1 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 | Open | M1 | Jourdain | 2 | 1 | 2
SCRs Submitted
P12846: eCL: Historical data that cannot match LAN ID for CSR & Submitter has issues |  | High | 5 | Open | M3 | Suzy | 5 | 32:00 | 0 |  |  |  | 2014-06-10
P12857: IQS - eCL Error Report not displaying errors from Verint feed |  | Urgent | 3 | Open | M3 | Dave | 3 | 15:10 | 3:25 |  |  |  | 2014-06-12
P12877: IQS/eCL/Scorecard - download of scorecard file to match on date |  | high | 2 | Closed | M1 | Bill | 0 | 7:00 | 0:50 |  |  |  | 2014-06-12 | 2014-06-30
P12897: eCL - Coaching Source request |  | Moderate | 4 | Closed | M1 | Suzy/Jourdain | 2 | 30:30 | 9:30 |  |  |  | 2014-06-13 | 2014-06-30
P12905: eCL - Inactivations Database task |  | Moderate | 0 | Closed | M1 | Dave | 0 | 0:00 | 1:30 |  |  |  | 2014-06-16 | 2014-06-19
P12922: IQS/eCL - Database missing eval ids from GDIT Data Feed files |  | high | 3 | Closed | M2 | Lola, Dave | 0 | 13:15 | 10:15 |  |  |  | 2014-06-17 | 2014-07-10
P12923: eCL - Inactivations need to inactivate records prior to May 5th |  | high | 0 | Closed | M1 | Suzy/Jourdain | 0 | 0 | 0:30 |  |  |  | 2014-06-17 | 2014-06-26
P12924: eCL - IQS update filter of records to send |  | high | 3 | Closed | M2 | Suzy,Dave | 0 | 14:10 | 8:50 |  |  |  | 2014-06-18 | 2014-07-10
P12926 : eCL - Admin task to remove duplicate records |  | high | 0 | Closed | M1 | Dave | 0 | 0 | 1:40 |  |  |  | 2014-06-18 | 2014-06-23
P12930: eCoaching Log - Display Verint scorecard name on eCL forms |  | high | 3 | Open | M2 | Suzy/Jourdain | 0 | 9:10 | 17:55 |  |  |  | 2014-06-18
P12957: eCoaching - Update procedure to set EmailSent flag to True on Notifications sent |  | high | 2 | Closed | M1 | Suzy | 0 | 2:35 | 1:47 |  |  |  | 2014-06-19 | 2014-06-23
P12962: CCO eCoaching - Coaching log Inactivations for Week of 06/23/2014 |  | high | 0 | Closed | M1 | Suzy | 0 | 0 | 2:00 |  |  |  | 2014-06-23 | 2014-07-07
P12963: eCL - Quality Filelist Count Loaded updated incorrectly |  | high | 4 | Closed | M2 | Suzy | 2 | 18:00 | 5:06 |  |  |  | 2014-06-23 | 2014-07-10
P12978: eCoaching - Update eCL Access Control Application to point to new eCoaching db |  | high | 2 | Closed | M1 | Suzy/Jourdain | 0 | 3:00 | 3:15 |  |  |  | 2014-06-23 | 2014-06-30
P12982: CCO eCoaching - Update Employee Hierarchy Load process |  | high | 3 | Closed | M2 | Suzy | 0 | 13:30 | 5:15 |  |  |  | 2014-06-24 | 2014-07-14
P12983: CCO eCoaching - Review and update Employee ID To lanID Table maintenance |  | high | 4 | Open | M3 | Suzy | 4 | 30:10 |  |  |  |  | 2014-06-24
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1
Phase II Work/Deliverables
User Stories | 1 | M |  | Open | I1 | Doug Stearns
Use Cases | 2 | M |  | Open | I1 | Doug Stearns
E1 Iteration Plan | 3 | M |  | Open |  | Tim Queen
Misc Current
Security

## M2-July
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M2 | Suzy/Jourdain | 1 | 2 | 1.5
Monthly Password Updates |  | H | 1 |  | M2 | Suzy/Jourdain | 1 | 1 | 1.5
Database Service Account Update |  | H | 1 |  | M2 | Jourdain | 2 | 1 | 1.5
SCRs Submitted
P13054: IQS/eCL - Added Scorecard Form name to data feed |  | high | 5 | Open | M2 | Dave/Suzy | 4 | 43:00 |  |  |  |  | 2014-07-01
P13071: CCO eCoaching - Create Indexes and Stats on eCoaching dtabase tables |  | Urgent | 3 | Closed | M2 | Suzy | 2 | 12:05 | 7:30 |  |  |  | 2014-07-02 | 2014-07-10
P13098: eCoaching - Update Source Dropdown Menu from Historical and Main Dashboard |  | moderate | 3 | Closed | M2 | Jourdain | 2 | 16:20 | 7:45 |  |  |  | 2014-07-08 | 2014-07-21
P13129: CCO eCoaching - Add ETS subcoaching reason under Attendance |  | high | 3 | Closed | M2 | Jourdain, Suzy | 1 | 16:05 | 12:40 |  |  |  | 2014-07-09 | 2014-07-21
P13136 CCO eCoaching - Manual coaching log inactivations for July |  | moderate | 0 | open | M2 | Suzy | 1 | 0 |  |  |  |  | 2014-07-10
P13138-eCoaching Log - Restrict submission of notifications for failed Verint scorecard |  | high | 4 | open | M3 | Suzy |  | 25:10 |  |  |  |  | 2014-07-10
P13213-eCL - Change coaching reason ID for OMR feed |  | moderate | 3 | open | M2 | Suzy |  | 12:50 |  |  |  |  | 2014-07-17
P13218-eCoaching - Update time stamps displayed to include Web Server Time Zone |  | moderate | 4 | open | M2 | jourdain |  | 36:10 |  |  |  |  | 2014-07-18
Misc Current
Security

## M3-Aug
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M3 | Suzy/Jourdain | 1 | 2 | 1.7
Monthly Password Updates |  | H | 1 |  | M3 | Suzy/Jourdain | 1 | 1 | 1
Database Service Account Update |  | H | 1 |  | M3 | Jourdain | 2 | 1 | 1.2
Phase II
Quality and Supervisor eCL | 1 | High |  | Completed |  | Suzy/Jourdain
SCRs Submitted/carried forward
P12846: eCL: Historical data that cannot match LAN ID for CSR & Submitter has issues |  | High | 5 | Close | M3 | Suzy | 5 | 32:00 | 21:15 |  |  |  | 2014-06-10 | 2014-08-14
P12857: IQS - eCL Error Report not displaying errors from Verint feed |  | Urgent | 3 | Close | M3 | Dave | 3 | 15:10 | 13:20 |  |  |  | 2014-06-12 | 2014-10-14
P12983: CCO eCoaching - Review and update Employee ID To lanID Table maintenance |  | high | 4 | Close | M3 | Suzy | 4 | 30:10 | 34:50 |  |  |  | 2014-06-24 | 2014-08-14
13263 - eCoaching - Update Coaching to allow other CSR job code users to submit coaching |  | Moderate | 4 | Close | M3 | Jourdain | 4 | 21:20 | 9:35 |  |  |  | 2014-07-25 | 2014-08-14
13265 - CCO eCoaching - Group multiple Coaching reasons for ecls in dashboard display |  | Moderate | 3 | Close | M3 | Suzy | 2 | 15:10 | 7:05 |  |  |  | 2014-07-25 | 2014-08-14
13276 - eCoaching Log -there are several references of bcc that should be changed to cco |  | Moderate | 4 | Hold | M4 | Jourdain | 4 | [5 empty] | 2014-07-30
Misc Current
Security

## M4-Sept
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 | Closed | M4 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 | Closed | M4 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 | Closed | M4 | Jourdain | 2 | 1 | 2
SCRs Submitted
13466 - Manual eCL inactivations for September | 1 |  | 1 | Pending Info | M4 | Suzy | 1 |  | 12:45 |  |  |  | 2014-09-02
13467 - User Checks on servers | 9 |  | 2 | dev | M5 | Tim | 2 | [5 empty] | 2014-09-02
13479 - Add CSR warning to eCL | 2 |  | 6 | Split Dev & V&V | M5 | Jourdain, Suzy | 6 | 101:30 | 5:30 |  |  |  | 2014-09-10
13506 - ARC CSRs to submit eCLs | 3 |  | 2 | Closed | M4 | Jourdain | 0 | 6:00 | 5:15 |  |  |  | 2014-09-12 | 2014-09-22
13512 - Display employee instead of CSR on all review pages | 4 |  | 3 | Closed | M4 | Jourdain | 0 | 24:10 | 11:45 |  |  |  | 2014-09-15 | 2014-09-25
13515 - update email notification mappings for sup and quality modules | 5 |  | 3 | Closed | M4 | Jourdain, Suzy | 0 | 28:10 | 15:35 |  |  |  | 2014-09-15 | 2014-10-06
13531 - update URL in notification script | 6 |  | 1 | Closed | M4 | Suzy | 0 | 1:00 | 0:30 |  |  |  | 2014-09-19 | 2014-09-25
13542 - Add warning question to eCL Supervisor | 8 |  |  | V&V | M6 | Doug, Jourdain, Suzy | [6 empty] | 2014-09-25
13549 - update eCL to remove PII | 7 |  | 0 | Closed | M4 | Suzy | 0 | 0 | 0:05 |  |  |  | 2014-09-29 | 2014-09-29
Misc Current
Security

## M5-Oct
Name / Description / | Ranking | Priority | Size estimate (Hours) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M5 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 |  | M5 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 |  | M5 | Jourdain | 2 | 1 | 2
SCRs Submitted
13571 - Fix incorrect submitterID values on eCLs | 1 |  | 0 | Closed | M5 | Suzy | 0 | 0 | 0:10 |  |  |  | 2014-10-03 | 2014-10-06
13609 - Add quality alignment specialists to receive eCLs | 2 |  | 6:20 | closed | M6 | Jourdain, Suzy, Doug |  |  | 3:15 |  |  |  | 2014-10-08 | 2014-11-10
13618 - CCO eCoaching - Update dashboards to add check for current lanid association | 3 |  | 36:10 | Dev | M6 | Jourdain, Suzy, Doug | [6 empty] | 2014-10-13
13622 - eCoaching - Review Page OMR Research SOP Link | 4 |  | 6:10 | closed | M6 | Jourdain, Suzy, Doug |  |  | 4:14 |  |  |  | 2014-10-14 | 2014-10-27
13623 - CCO eCoaching - Load process for historical warning logs | 5 |  |  | IA review | M7 | Jourdain, Suzy, Doug | [6 empty] | 2014-10-14
13624 - eCoaching - Warnings to be inactivated after 13 weeks | 6 |  | 16:10 | Implementation | M5 | Jourdain, Suzy, Doug |  |  | 15:00 |  |  |  | 2014-10-14
13631 - eCoaching - Coaching Notes overwritten | 7 |  | 34:40 | Dev | M7 | Jourdain, Suzy, Doug | [6 empty] | 2014-10-14
13653 - eCoaching - LSA Module | 8 |  | 101:10 | Dev | M8 | Jourdain, Suzy, Doug | [6 empty] | 2014-10-16
13659 - eCoaching - ETS data feed | 9 |  | 100:10 | Dev | M6 | Jourdain, Suzy, Doug | [6 empty] | 2014-10-16
13694 - CCO eCoaching - Fix incorrect submitterid value for IQS logs | 10 |  | 0:00 | closed | M5 | Suzy |  |  | 0:20 |  |  |  | 2014-10-20 | 2014-10-27
13753 - eCoaching - grant rights to the Operations SR. Exec Mgmt | 11 |  | 16:10 | closed | M5 | Suzy |  |  | 9:10 |  |  |  | 2014-10-28 | 2014-11-13
13759 - eCoaching Log - mask/handle names with apostrophe in dashboard sorting queries. | 12 |  | 12:10 | Dev | M5 | Suzy, doug | [6 empty] | 2014-10-31
Misc Current
Security

## M6-Nov
Name / Description / | Ranking | Priority | Size estimate (Hourss) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M6 | Suzy/Jourdain | 1 | 2
Monthly Password Updates |  | H | 1 |  | M6 | Suzy/Jourdain | 1 | 1
Database Service Account Update |  | H | 1 |  | M6 | Jourdain | 2 | 1
SCRs Submitted
13794 - eCoaching Log - Update supervisor pending to allow for acting manager view | 1 |  | 9:40 | Dev | M6 | Doug, Suzy | [6 empty] | 2014-11-07
13822 - eCoaching - Disable review for ARCs on My Submissions page | 2 |  | 16:40 | Dev | M6 | Suzy, Doug, Jourdain | [6 empty] | 2014-11-12
13833 - eCoaching - Changing employee causes different results with Warnings | 3 |  | 13:05 | Dev | M6 | Jourdain, Doug | [6 empty] | 2014-11-13
Security

## M7-Dec
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M7 | Suzy/Jourdain | 1 | 2 | 2
Monthly Password Updates |  | H | 1 |  | M7 | Suzy/Jourdain | 1 | 1 | 1.2
Database Service Account Update |  | H | 1 |  | M7 | Jourdain | 2 | 1 | 2
SCRs Submitted
Misc Current
Security

## M8-Jan
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M8 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M8 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M8 | Jourdain
Migration to AD
Escalated Issues
Production Support
SCRs Submitted
Misc Current
Security

## M9-Feb
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M9 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M9 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M9 | Jourdain
Migration to AD
Escalated Issues
Production Support
SCRs Submitted
Misc Current
Security

## M10-March
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M10 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M10 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M10 | Jourdain
SCRs Submitted
Misc Current
Security

## M11-April
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M11 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M11 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M11 | Jourdain
SCRs Submitted
Misc Current
Security

## M12-May
Name / Description / | Ranking | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (points) | Iteration Planned Hours | Hours worked | Reference material | Dependancies | Source activity1 | Submit Date | Completion Date
Recurring Work
Monthly Security Patching |  | H | 1 |  | M12 | Suzy/Jourdain
Monthly Password Updates |  | H | 1 |  | M12 | Suzy/Jourdain
Database Service Account Update |  | H | 1 |  | M12 | Jourdain
SCRs Submitted
Misc Current
Security