## Sheet1
Project: CCO Engineering Server: f3420-tfsasp01\CCO Program Query: All eCL WIT Q2 List type: Tree
ID | Column2 | Work Item Type | Severity | Created Date | Closed Date | Title 1 | Title 2 | Title 3 | Assigned To | State | Original Estimate | Completed Work | Remaining Work
5085 | Problem Report | Problem Report | 1 - Critical | 2016-12-29 10:05 | 2017-01-05 13:00 | eCoaching - IQS logs not getting selected for notifications |  |  | Miller, Jackie K | Closed | 7.2 | 6 | 0
5484 | Task | Task | 2 - High | 2017-02-02 15:16 | 2017-02-16 13:47 | eCoaching - Update the coaching log reason for null values |  |  | Miller, Jackie K | Closed | 1.9 | 2.1 | 0
5712 | Task | Task | 2 - High | 2017-02-20 16:49 | 2017-02-23 13:24 | eCoaching - Admin task - Reassign coaching logs to correct supervisor |  |  | Miller, Jackie K | Closed | 1.5 | 1.5 | 0
5721 | Task | Task | 2 - High | 2017-02-21 08:26 | 2017-02-23 13:24 | eCoaching - add Verint id to description of recently generated NPN logs |  |  | Miller, Jackie K | Closed | 6.7 | 6.2 | 0
4904 | Requirement | Requirement | 2 - High | 2016-12-06 14:35 | 2017-01-17 09:37 | eCoaching - Manually archive coaching logs to reduce size of 'active' database records |  |  | Ingram, Michael T | Closed |  | 8.9
5309 | Change Request | Change Request | 2 - High | 2017-01-23 13:56 | 2017-02-13 14:34 | eCoaching - New feed from Quality for generating coaching logs |  |  | Miller, Jackie K | Closed | 27.3 | 15.8 | 0
5365 | Change Request | Change Request | 2 - High | 2017-01-26 16:13 | 2017-02-13 14:14 | eCoaching - Allow those with job code WPOP80 access to the historical dashboard |  |  | Miller, Jackie K | Closed | 6.3 | 5.3 | 0
5649 | Change Request | Change Request | 2 - High | 2017-02-16 10:03 | 2017-02-23 13:24 | eCoaching - NPN Quality feed to pull description text from database based on #NPN code passed in feed file |  |  | Miller, Jackie K | Closed | 20.8 | 13.4 | 0
3397 | Task | Task | 3 - Medium | 2016-07-25 08:09 | 2016-08-05 09:05 | eCL - Reassigned Reviewer Not Able to Edit the Log on Review Page |  |  | Huang, Lili | Closed | 6 | 6 | 0
4909 | Task | Task | 3 - Medium | 2016-12-07 09:57 | 2016-12-08 12:21 | ecl Historical Dashboard Control Access web app - Will need to create/use its own app pool on web server |  |  | Miller, Jackie K | Closed | 1.8 | 1.7 | 0
5406 | Task | Task | 3 - Medium | 2017-01-31 07:49 | 2017-02-02 14:17 | eCoaching - Add Time Calc App documentation to TFS source control |  |  | Miller, Jackie K | Closed | 1.4 | 0.8 | 0
4897 | Change Request | Requirement | 3 - Medium | 2017-06-17 | 2017-01-17 09:35 | eCoaching - Implement dashboard for senior managers (SRMGR) |  |  | Ingram, Michael T | Closed |  | 325.5
4899 | Research | Requirement | 3 - Medium | 2017-07-06 | 2017-02-07 09:39 | eCoaching - research the appropriate indexes needed to improve performance |  |  | Ingram, Michael T | Closed | 20 | 15
4901 | Change Request | Requirement | 3 - Medium | 2016-07-12 | 2016-12-22 10:31 | eCoaching - email notification when logs are completed |  |  | Ingram, Michael T | Closed |  | 32.8
5539 | Problem Report | Problem Report | 3 - Medium | 2017-02-07 10:58 | 2017-03-06 13:55 | eCoaching - misspelled value of Opportun!ty or Re!nforcement |  |  | Miller, Jackie K | Closed | 12.8 | 11.8 | 0
4916 | Change Request | Change Request | 3 - Medium | 2016-12-08 10:26 | 2016-12-19 13:49 | eCoaching - Generic Feed |  |  | Ingram, Michael T | Closed | 28.5 | 33.9 | 0
5353 | Change Request | Change Request | 3 - Medium | 2017-01-25 08:14 | 2017-02-13 14:34 | eCoaching - Update indexes in Coaching database |  |  | Miller, Jackie K | Closed | 7.9 | 17.6 | 0
5653 | Change Request | Change Request | 3 - Medium | 2017-02-16 10:13 | 2017-03-16 13:30 | eCoaching - Create new NPN coaching logs from existing quality submitted scorecard logs |  |  | Miller, Jackie K | Closed | 43 | 36.8 | 0
5756 | Change Request | Change Request | 3 - Medium | 2017-02-24 07:47 | 2017-03-09 13:23 | eCoaching - Admin tool access for jobcode WPPM50 |  |  | Miller, Jackie K | Closed | 13.3 | 7.7 | 0
4852 | Task | Task | 4 - Low | 2016-12-01 15:08 | 2017-01-05 13:00 | eCoaching - Admin Task - Manual inactivations for December 2016 |  |  | Miller, Jackie K | Closed | 2.2 | 2.2 | 0
5126 | Task | Task | 4 - Low | 2017-01-03 11:17 | 2017-02-02 14:13 | eCoaching - Admin Task - Manual inactivations for January 2017 |  |  | Miller, Jackie K | Closed | 2.2 | 3.2 | 0
5147 | Task | Task | 4 - Low | 2017-01-04 08:30 | 2017-01-12 13:35 | eCoaching - Moving unused eCL requirements documents to obsolete folder and other TFS cleanup |  |  | Miller, Jackie K | Closed | 9.7 | 3 | 0
5149 | Task | Task | 4 - Low | 2017-01-04 08:50 | 2017-01-12 13:35 | eCoaching - Requirement document consolidation, cleanup, and updates |  |  | Miller, Jackie K | Closed | 20.3 | 12.2 | 0
5223 | Task | Task | 4 - Low | 2017-01-12 08:40 | 2017-01-30 15:00 | eCoaching - Admin Task - Cleanup database documentation |  |  | Miller, Jackie K | Closed | 18.4 | 17.4 | 0
5294 | Task | Task | 4 - Low | 2017-01-19 10:26 | 2017-01-24 08:12 | eCoaching - Admin Task - New TFS subdirectories and file moves |  |  | Miller, Jackie K | Closed | 6.7 | 6.9 | 0
5452 | Task | Task | 4 - Low | 2017-02-02 08:38 | 2017-03-02 13:56 | eCoaching - Admin Task - Manual inactivations for February 2017 |  |  | Miller, Jackie K | Closed | 2.1 | 1.5 | 0
5420 | Change Request | Change Request | 2 - High | 2017-01-31 13:50 |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting |  |  | Miller, Jackie K | Active | 103 | 56 | 47.2
5421 | Change Request | Change Request | 2 - High | 2017-01-31 13:54 |  | eCoaching - Create monthly summary ecoaching reports for each ecl module |  |  | Miller, Jackie K | Active | 139.3 | 57.8 | 73
5621 | Change Request | Change Request | 3 - Medium | 2017-02-14 10:48 |  | eCoaching - Initial ad hoc reporting for eCL |  |  | Miller, Jackie K | Active | 77.6 | 19.1 | 58
5641 | Change Request | Change Request | 3 - Medium | 2017-02-15 13:26 |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool |  |  | Miller, Jackie K | Active | 42.8 | 28 | 17.3
5642 | Change Request | Change Request | 3 - Medium | 2017-02-15 13:31 |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool |  |  | Miller, Jackie K | Active | 60.8 | 2.6 | 57.7

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | 2017-03-02 13:56 | value doesn't matter | \ | \ | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Closed | CAPA | Select User... | Active | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | 1 - Critical | Active
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | \Aspect | \Assignment and Exception | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Closed | Augustin, Jourdain M | Design | CAPA Action | Augustin, Jourdain M | Closed | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | Closed
|  |  |  | \Assignment and Exception Tracking System | \Assignment and Exception\A_E 2015 | Black, Karen S | Proposed | Black, Karen S | VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_C0-8B-87-81-67-52-71-76-29-2A-B8-4D-FB-D4-D6-6F-1E-E5-D9-2A | Black, Karen S | Proposed | Black, Karen S | Proposed | Black, Karen S | Proposed | Black, Karen S | Proposed | Black, Karen S | Proposed | Black, Karen S | Hold | Black, Karen S | Proposed | Black, Karen S | Resolved | Black, Karen S | Proposed | Black, Karen S | Proposed | Black, Karen S | Ready | Change Request | Black, Karen S | Proposed | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | 3 - Medium | Proposed
|  |  |  | \Attendance Tracking Tool | \Assignment and Exception\A_E 2015\A_E 2015-10 | Borkowski, Steve T | Resolved | Borkowski, Steve T |  | Borkowski, Steve T | Resolved | Borkowski, Steve T | Resolved | Borkowski, Steve T | Resolved | Borkowski, Steve T | Resolved | Borkowski, Steve T | Resolved | Borkowski, Steve T | Proposed | Borkowski, Steve T | Resolved | Borkowski, Steve T | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Review_System.State | Borkowski, Steve T | Resolved | Borkowski, Steve T | Resolved | Borkowski, Steve T | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Test Case_System.State | Feature | Borkowski, Steve T | Resolved | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | Resolved
|  |  |  | \Business Rule | \Assignment and Exception\A_E 2015\A_E 2015-11 | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_CAPA_System.State | Coughlin, Brian E |  | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_CAPA Action_System.State | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Change Request_System.State | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Feature_System.State | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Impact Assessment_System.State | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Issue_System.State | Coughlin, Brian E | Resolved | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Requirement_System.State | Coughlin, Brian E |  | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Risk_System.State | Coughlin, Brian E | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Task_System.State | Coughlin, Brian E |  | Impact Assessment | Coughlin, Brian E | Hold | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_CAPA_Microsoft.VSTS.Common.Severity | VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_45-F5-9C-27-95-2A-7B-65-33-77-4B-A9-8C-81-2F-7D-A7-A1-56-F2 | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_CAPA Action_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Change Request_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Impact Assessment_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Issue_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Problem Report_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Requirement_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Risk_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Task_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Test Case_Microsoft.VSTS.Common.Severity | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Microsoft.VSTS.Common.Severity | VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_F9-E1-2C-98-86-04-E5-7D-4B-B1-8B-C7-8F-D4-55-95-91-76-6C-DD
|  |  |  | \Casework Management Tool | \Assignment and Exception\A_E 2015\A_E 2015-12 | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Problem Report_System.State | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Dye, Ellen |  | Issue | Dye, Ellen | Design
|  |  |  | \eCoaching Log | \Assignment and Exception\A_E 2016 | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Erickson, William T |  | Problem Report | Erickson, William T | Ready
|  |  |  | \Exclusion Super User Group Team | \Assignment and Exception\A_E 2016\A_E 2016-01 | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Gilman, Joseph R |  | Requirement | Gilman, Joseph R | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_System.State
|  |  |  | \Functional | \Assignment and Exception\A_E 2016\A_E 2016-02 | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Haltmeyer, Jacqueline K |  | Review | Haltmeyer, Jacqueline K
|  |  |  | \Interface | \Assignment and Exception\A_E 2016\A_E 2016-03 | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Hinman, David L |  | Risk | Hinman, David L
|  |  |  | \Outbound Analysis and Reporting | \Assignment and Exception\A_E 2016\A_E 2016-04 | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Huang, Lili |  | Task | Huang, Lili
|  |  |  | \Performance Management | \Assignment and Exception\A_E 2016\A_E 2016-05 | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Hutson, James E |  | Test Case | Hutson, James E
|  |  |  | \Quality | \Assignment and Exception\A_E 2016\A_E 2016-06 | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | Ingram, Michael T |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_System.WorkItemType | Ingram, Michael T
|  |  |  | \Security | \Assignment and Exception\A_E 2016\A_E 2016-07 | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  | Keune, Leslie A |  |  | Keune, Leslie A
|  |  |  | \Telecom | \Assignment and Exception\A_E 2016\A_E 2016-08 | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  | Miller, Jackie K |  |  | Miller, Jackie K
|  |  |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_System.AreaPath | \Assignment and Exception\A_E 2016\A_E 2016-09 | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  | Mishra, Lex S |  |  | Mishra, Lex S
[5 empty] | \Assignment and Exception\A_E 2016\A_E 2016-10 | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  | Moharar, Kalyan |  |  | Moharar, Kalyan
[5 empty] | \Assignment and Exception\A_E 2016\A_E 2016-11 | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  | Palacherla, Susmitha C |  |  | Palacherla, Susmitha C
[5 empty] | \Assignment and Exception\A_E 2016-12 | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  | Pemberton, Brian R |  |  | Pemberton, Brian R
[5 empty] | \Assignment and Exception\A_E 2017-01 | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  | Queen, Timothy K |  |  | Queen, Timothy K
[5 empty] | \Assignment and Exception\A_E 2017-02 | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  | Reem, James P |  |  | Reem, James P
[5 empty] | \Assignment and Exception\A_E 2017-03 | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  | Shown, James B |  |  | Shown, James B
[5 empty] | \Assignment and Exception\A_E 2017-04 | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  | Stearns, Douglas R |  |  | Stearns, Douglas R
[5 empty] | \Attendance Tracking Tool | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  | Stein, Lisa D |  |  | Stein, Lisa D
[5 empty] | \Attendance Tracking Tool\ATT 2015 | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  | Szabo, Brian P |  |  | Szabo, Brian P
[5 empty] | \Attendance Tracking Tool\ATT 2015\ATT 2015-10 | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  | Treinen, Lola R |  |  | Treinen, Lola R
[5 empty] | \Attendance Tracking Tool\ATT 2015\ATT 2015-11 | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_CAPA_System.AssignedTo |  | VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_C8-2A-0B-0C-74-2F-83-66-DD-CF-90-6F-A5-23-5B-FE-6A-69-BD-E6 |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_CAPA Action_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Change Request_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Feature_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Impact Assessment_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Issue_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Problem Report_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Requirement_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Review_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Risk_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Task_System.AssignedTo |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_Test Case_System.AssignedTo |  |  | all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_System.AssignedTo
\Attendance Tracking Tool\ATT 2015\ATT 2015-12
\Attendance Tracking Tool\ATT 2016
\Attendance Tracking Tool\ATT 2016\ATT 2016-01
\Attendance Tracking Tool\ATT 2016\ATT 2016-02
\Attendance Tracking Tool\ATT 2016\ATT 2016-03
\Attendance Tracking Tool\ATT 2016\ATT 2016-04
\Attendance Tracking Tool\ATT 2016\ATT 2016-05
\Attendance Tracking Tool\ATT 2016\ATT 2016-06
\Attendance Tracking Tool\ATT 2016\ATT 2016-07
\Attendance Tracking Tool\ATT 2016\ATT 2016-08
\Attendance Tracking Tool\ATT 2016\ATT 2016-09
\Attendance Tracking Tool\ATT 2016\ATT 2016-10
\Attendance Tracking Tool\ATT 2016\ATT 2016-11
\Attendance Tracking Tool\ATT 2016-12
\Attendance Tracking Tool\ATT 2017-01
\Attendance Tracking Tool\ATT 2017-02
\Attendance Tracking Tool\ATT 2017-03
\Attendance Tracking Tool\ATT 2017-04
\Attendance Tracking Tool\ATT 2017-05
\Attendance Tracking Tool\ATT Backlog
\Backlog
\Casework Management Tool
\Casework Management Tool\CMT 2016-11
\Casework Management Tool\CMT 2016-12
\Casework Management Tool\CMT 2017-01
\Casework Management Tool\CMT 2017-02
\Casework Management Tool\CMT 2017-03
\Casework Management Tool\CMT 2017-04
\Casework Management Tool\CMT 2017-05
\Casework Management Tool\CMT Backlog
\eCoaching Log
\eCoaching Log\eCL 2015
\eCoaching Log\eCL 2015\eCL 2015-10
\eCoaching Log\eCL 2015\eCL 2015-11
\eCoaching Log\eCL 2015\eCL 2015-12
\eCoaching Log\eCL 2016
\eCoaching Log\eCL 2016\eCL 2016-01
\eCoaching Log\eCL 2016\eCL 2016-02
\eCoaching Log\eCL 2016\eCL 2016-03
\eCoaching Log\eCL 2016\eCL 2016-04
\eCoaching Log\eCL 2016\eCL 2016-05
\eCoaching Log\eCL 2016\eCL Q1
\eCoaching Log\eCL 2016\eCL Q2
\eCoaching Log\eCL Backlog
\eCoaching Log\eCL Q3
\eCoaching Log\eCL Q4
\Iteration 1
\New Project Startup
\Outbound Analysis and Reporting
\Outbound Analysis and Reporting\OAR 2015-10
\Outbound Analysis and Reporting\OAR 2015-11
\Outbound Analysis and Reporting\OAR 2015-12
\Outbound Analysis and Reporting\OAR 2016-01
\Outbound Analysis and Reporting\OAR 2016-02
\Outbound Analysis and Reporting\OAR 2016-03
\Outbound Analysis and Reporting\OAR 2016-04
\Outbound Analysis and Reporting\OAR 2016-05
\Performance Management Scorecard
\Performance Management Scorecard\PM 2015
\Performance Management Scorecard\PM 2015\PM 2015-10
\Performance Management Scorecard\PM 2015\PM 2015-11
\Performance Management Scorecard\PM 2015\PM 2015-12
\Performance Management Scorecard\PM 2016
\Performance Management Scorecard\PM 2016\PM 2016-01
\Performance Management Scorecard\PM 2016\PM 2016-02
\Performance Management Scorecard\PM 2016\PM 2016-03
\Performance Management Scorecard\PM 2016\PM 2016-04
\Performance Management Scorecard\PM 2016\PM 2016-05
\Performance Management Scorecard\PM 2016\PM 2016-06
\Performance Management Scorecard\PM 2016\PM 2016-07
\Performance Management Scorecard\PM 2016\PM 2016-08
\Performance Management Scorecard\PM 2016\PM 2016-09
\Performance Management Scorecard\PM 2016-10
\Performance Management Scorecard\PM 2016-11
\Performance Management Scorecard\PM 2016-12
\Performance Management Scorecard\PM 2017-01
\Performance Management Scorecard\PM 2017-02
\Performance Management Scorecard\PM 2017-03
\Performance Management Scorecard\PM 2017-04
\Performance Management Scorecard\PM 2017-05
\Performance Management Scorecard\PM Backlog
all_VSTS_34f8be27_2cf6_42c2_8e85_94c7b7da262c_System.IterationPath