## Sheet1
Project: CCO Engineering Server: f3420-tfsasp01\CCO Program Query: Open Parent Records with Requirements and with active eCL child records List type: Tree
ID | Created Date | Created By | Work Item Type | Title 1 | Title 2 | Title 3 | Functional Area | Discipline | Security Impact | Assigned To | State | Reason | Requirement Type | Source of Request | Area Path | Iteration Path | RM Priority | CM Priority | Severity | Complexity | Original Estimate | Remaining Work | Completed Work | History
5420 | 2017-01-31 13:50 | Stearns, Douglas R | Change Request | eCoaching - Create infrastructure within ecl admin tool to allow for reporting |  |  | [eCoaching] |  | No | Miller, Jackie K | Active | Pending Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 103 | 59.2 | 43.4
|  | Miller, Jackie K | Requirement |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting |  | [eCoaching] |  | No | Ingram, Michael T | Proposed | New | Business Process | Test Engineer | \eCoaching Log | \eCoaching Log\eCL Q4 | 2 - High |  | 2 - High | Moderate
|  | Miller, Jackie K | Task |  |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (R&T) | [eCoaching] | Requirements | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 2 - High | 2 - High | Moderate | 6 | 6
|  | Miller, Jackie K | Task |  |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (V&V) | [eCoaching] | Test | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 2 - High | 2 - High | Moderate | 13.2 | 13.2
|  | Miller, Jackie K | Task |  | ` | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (DB Dev) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 2 - High | 2 - High | Moderate | 30 | 30
|  | Miller, Jackie K | Task |  |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (UI Dev) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 2 - High | 2 - High | Moderate | 10 | 10
5474 | 2017-02-02 14:49 | Miller, Jackie K | Requirement |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting |  | [eCoaching] |  | No | Ingram, Michael T | Closed | Closed | Business Process | Test Engineer | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate |  |  | 43.4
5475 | 2017-02-02 14:50 | Miller, Jackie K | Task |  |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (R&T) | [eCoaching] | Requirements | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 9.2 | 6 | 3.2
5476 | 2017-02-02 14:52 | Miller, Jackie K | Task |  |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (V&V) | [eCoaching] | Test | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 13.2 | 13.2 | 0.2
5477 | 2017-02-02 14:53 | Miller, Jackie K | Task |  |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (DB Dev) | [eCoaching] | Development | No | Palacherla, Susmitha C | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 40 | 30 | 10
5478 | 2017-02-02 14:54 | Miller, Jackie K | Task |  |  | eCoaching - Create infrastructure within ecl admin tool to allow for reporting (UI Dev) | [eCoaching] | Development | No | Huang, Lili | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 40 | 10 | 30
5421 | 2017-01-31 13:54 | Stearns, Douglas R | Change Request | eCoaching - Create monthly summary ecoaching reports for each ecl module |  |  | [eCoaching] |  | No | Miller, Jackie K | Active | Pending Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 139.3 | 41.5 | 46.9
|  | Miller, Jackie K | Requirement |  | eCoaching - Create monthly summary ecoaching reports for each ecl module |  | [eCoaching] |  | No | Ingram, Michael T | Proposed | New | Business Process | Test Engineer | \eCoaching Log | \eCoaching Log\eCL Q4 | 2 - High |  | 2 - High | Moderate
|  | Miller, Jackie K | Task |  |  | eCoaching - Create monthly summary ecoaching reports for each ecl module (R&T) | [eCoaching] | Requirements | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 2 - High | 2 - High | Moderate | 7.1 | 7.1
|  | Miller, Jackie K | Task |  |  | eCoaching - Create monthly summary ecoaching reports for each ecl module (V&V) | [eCoaching] | Test | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 2 - High | 2 - High | Moderate | 14.4 | 14.4
|  | Miller, Jackie K | Task |  |  | eCoaching - Create monthly summary ecoaching reports for each ecl module (UI Dev) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 2 - High | 2 - High | Moderate | 20 | 20
5479 | 2017-02-02 14:55 | Miller, Jackie K | Requirement |  | eCoaching - Create monthly summary ecoaching reports for each ecl module |  | [eCoaching] |  | No | Ingram, Michael T | Closed | Closed | Business Process | Test Engineer | \eCoaching Log | \eCoaching Log\eCL Q3 | 2 - High |  | 2 - High | Moderate |  |  | 46.9
5480 | 2017-02-02 14:57 | Miller, Jackie K | Task |  |  | eCoaching - Create monthly summary ecoaching reports for each ecl module (R&T) | [eCoaching] | Requirements | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 13.2 | 7.1 | 6.1
5481 | 2017-02-02 14:58 | Miller, Jackie K | Task |  |  | eCoaching - Create monthly summary ecoaching reports for each ecl module (V&V) | [eCoaching] | Test | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 15.2 | 14.4 | 0.8
5483 | 2017-02-02 15:00 | Miller, Jackie K | Task |  |  | eCoaching - Create monthly summary ecoaching reports for each ecl module (UI Dev) | [eCoaching] | Development | No | Huang, Lili | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 2 - High | 2 - High | Moderate | 60 | 20 | 40
5621 | 2017-02-14 10:48 | Stearns, Douglas R | Change Request | eCoaching - Initial ad hoc reporting for eCL |  |  | [eCoaching] |  | No | Miller, Jackie K | Active | Pending Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 77.6 | 74.3 | 2.8
|  | Miller, Jackie K | Requirement |  | eCoaching - Initial ad hoc reporting for eCL |  | [eCoaching] |  | No | Ingram, Michael T | Proposed | New | Business Process | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q4 | 3 - Moderate |  | 3 - Medium | Moderate
|  | Miller, Jackie K | Task |  |  | eCoaching - Initial ad hoc reporting for eCL (R&T) | [eCoaching] | Requirements | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 13.3 | 13.3
|  | Miller, Jackie K | Task |  |  | eCoaching - Initial ad hoc reporting for eCL (Dev) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 46.5 | 46.5
|  | Miller, Jackie K | Task |  |  | eCoaching - Initial ad hoc reporting for eCL (V&V) | [eCoaching] | Test | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 14.5 | 14.5
5663 | 2017-02-16 14:04 | Miller, Jackie K | Requirement |  | eCoaching - Initial ad hoc reporting for eCL |  | [eCoaching] |  | No | Ingram, Michael T | Closed | Closed | Business Process | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q3 | 3 - Moderate |  | 3 - Medium | Moderate |  |  | 2
5664 | 2017-02-16 14:05 | Miller, Jackie K | Task |  |  | eCoaching - Initial ad hoc reporting for eCL (R&T) | [eCoaching] | Requirements | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 15.3 | 13.3 | 2
5665 | 2017-02-16 14:06 | Miller, Jackie K | Task |  |  | eCoaching - Initial ad hoc reporting for eCL (Dev) | [eCoaching] | Development | No | Palacherla, Susmitha C | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 46.5 | 46.5 | 0
5666 | 2017-02-16 14:07 | Miller, Jackie K | Task |  |  | eCoaching - Initial ad hoc reporting for eCL (V&V) | [eCoaching] | Test | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 14.5 | 14.5 | 0
5641 | 2017-02-15 13:26 | Stearns, Douglas R | Change Request | eCoaching - Move the functionality of the current Delete Log to the Admin Tool |  |  | [eCoaching] |  | No | Miller, Jackie K | Active | Pending Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 42.8 | 23.3 | 22
|  | Miller, Jackie K | Requirement |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool |  | [eCoaching] |  | No | Ingram, Michael T | Proposed | New | Functional | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q4 | 3 - Moderate |  | 3 - Medium | Moderate
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (UI DEV) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 8 | 8
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (DB DEV) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 10 | 10
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (R&T) | [eCoaching] | Requirements | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 1.6 | 1.6
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (V&V) | [eCoaching] | Test | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 3.7 | 3.7
5692 | 2017-02-20 13:54 | Stein, Lisa D | Requirement |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool |  | [eCoaching] |  | No | Ingram, Michael T | Closed | Closed | Functional | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q3 | 3 - Moderate |  | 3 - Medium | Moderate |  |  | 21.1
5693 | 2017-02-20 13:55 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (UI DEV) | [eCoaching] | Development | No | Huang, Lili | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 21 | 8 | 16
5694 | 2017-02-20 13:56 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (UI DD) | [eCoaching] | Development | No | Huang, Lili | Closed | Dev and V&V Complete |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 4 | 0 | 4
5695 | 2017-02-20 13:57 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (DB DEV) | [eCoaching] | Development | No | Palacherla, Susmitha C | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 10 | 10 | 0
5697 | 2017-02-20 13:59 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (R&T) | [eCoaching] | Requirements | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 2.7 | 1.6 | 1.1
5698 | 2017-02-20 14:00 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Delete Log to the Admin Tool (V&V) | [eCoaching] | Test | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 3.7 | 3.7 | 0
5642 | 2017-02-15 13:31 | Stearns, Douglas R | Change Request | eCoaching - Move the functionality of the current Access Control List to the Admin Tool |  |  | [eCoaching] |  | No | Miller, Jackie K | Active | Pending Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 60.8 | 57.7 | 2.6
|  | Miller, Jackie K | Requirement |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool |  | [eCoaching] |  | No | Ingram, Michael T | Proposed | New | Functional | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q4 | 2 - High |  | 3 - Medium | Moderate
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (UI DEV) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 35 | 35
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (UI DD) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 8 | 8
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (DB Dev) | [eCoaching] | Development | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 9 | 9
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (R&T) | [eCoaching] | Requirements | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 1 | 1
|  | Miller, Jackie K | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (V&V) | [eCoaching] | Test | No | Miller, Jackie K | Proposed | Submit Dev and V&V |  |  | \eCoaching Log | \eCoaching Log\eCL Q4 |  | 3 - Moderate | 3 - Medium | Moderate | 4.7 | 4.7
5699 | 2017-02-20 14:03 | Stein, Lisa D | Requirement |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool |  | [eCoaching] |  | No | Ingram, Michael T | Closed | Closed | Functional | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q3 | 3 - Moderate |  | 3 - Medium | Moderate |  |  | 1.7
5700 | 2017-02-20 14:04 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (UI DEV) | [eCoaching] | Development | No | Huang, Lili | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 35 | 35 | 0
5701 | 2017-02-20 14:05 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (UI DD) | [eCoaching] | Development | No | Huang, Lili | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 8 | 8 | 0
5702 | 2017-02-20 14:06 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (DB Dev) | [eCoaching] | Development | No | Palacherla, Susmitha C | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 9 | 9 | 0
5704 | 2017-02-20 14:08 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (R&T) | [eCoaching] | Requirements | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 2.7 | 1 | 1.7
5705 | 2017-02-20 14:09 | Stein, Lisa D | Task |  |  | eCoaching - Move the functionality of the current Access Control List to the Admin Tool (V&V) | [eCoaching] | Test | No | Stearns, Douglas R | Closed | Work Not Completed. Moving Remaining Work to the Next Iteration |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 4.7 | 4.7 | 0
5653 | 2017-02-16 10:13 | Stearns, Douglas R | Change Request | eCoaching - Create new NPN coaching logs from existing quality submitted scorecard logs |  |  | [eCoaching] |  | No | Miller, Jackie K | Active | Pending Implementation |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Moderate | 43 | 0.5 | 35.7
5706 | 2017-02-20 14:12 | Stein, Lisa D | Requirement |  | eCoaching - Create new NPN coaching logs from existing quality submitted scorecard logs |  | [eCoaching] |  | No | Ingram, Michael T | Closed | Closed | Functional | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q3 | 3 - Moderate |  | 3 - Medium | Moderate
5756 | 2017-02-24 07:47 | Palacherla, Susmitha C | Change Request | eCoaching - Admin tool access for jobcode WPPM50 |  |  | [eCoaching] |  | No | Miller, Jackie K | Active | Pending Implementation |  |  | \eCoaching Log | \eCoaching Log\eCL Q3 |  | 3 - Moderate | 3 - Medium | Easy | 13.3 | 0.5 | 6.2
5840 | 2017-03-02 14:04 | Miller, Jackie K | Requirement |  | eCoaching - Admin tool access for jobcode WPPM50 |  | [eCoaching] |  | No | Ingram, Michael T | Closed | Closed | Business Process | Program Manager | \eCoaching Log | \eCoaching Log\eCL Q3 | 3 - Moderate |  | 3 - Medium | Easy

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Select User... | [Arrival Time] | No | Active | Active | Accepted | Select User... | Active | Accepted | Select User... | [Arrival Time] | No | Active | Abandoned | Select User... | [Arrival Time] | Active | Abandoned | Select User... | [Arrival Time] | No | Active | Additional Assessment requested | Select User... | [Arrival Time] | No | Active | Accepted | Select User... | [Arrival Time] | No | Active | Approved | Select User... | [Arrival Time] | No | Active | Abandoned | Business Process | Select User... | [Arrival Time] | Active | Accepted (as is) | Select User... | [Arrival Time] | No | Active | Accepted (won't mitigate) | Select User... | Access Change Request | [Arrival Time] | No | Active | Admin Task V&V Complete | Select User... | [Arrival Time] | Closed | CCB approved to Close | Select User... | CAPA | Active | Accepted | [Arrival Time] | No | Business Process | Access Change Request | Access Change Request | Business Process | Select User... | CAPA | Proposed | CCB Review | 0 - Unassigned | 1 - Critical | 0 - Unassigned | Difficult | 1 - Critical | 0 - Unassigned | 1 - Critical | Difficult | Difficult | 1 - Critical | Difficult | 1 - Critical | Difficult | 1 - Critical | Difficult | 1 - Critical | Difficult | 1 - Critical | Difficult | 1 - Critical | Difficult | 1 - Critical | Difficult | 1 - Critical | 1 - Critical | CCB Review | 0 - Unassigned | 0 - Unassigned | 0 - Unassigned | 0 - Unassigned | 0 - Unassigned | 0 - Unassigned | 0 - Unassigned | 0 - Unassigned | 0 - Unassigned | Abandoned | Architecture | Architecture | Architecture | Architecture | CCB Review | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Select User... | Architect | Architect | Architect | Select User... | Active | Administrative Task Complete
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | \Aspect | \Assignment and Exception | Augustin, Jourdain M | [Aspect] | Yes | Closed | Closed | Closed in Error | Augustin, Jourdain M | Closed | Closed in Error | Augustin, Jourdain M | [Aspect] | Yes | Closed | Accepted | Augustin, Jourdain M | [Aspect] | Closed | Acceptance tests fail | Augustin, Jourdain M | [Aspect] | Yes | Closed | Approved | Augustin, Jourdain M | [Aspect] | Yes | Closed | CCB Review | Augustin, Jourdain M | [Aspect] | Yes | Closed | As Designed | Augustin, Jourdain M | [Aspect] | Yes | Closed | Accepted | Business Rule | Augustin, Jourdain M | [Aspect] | Closed | Accepted with Major Changes | Augustin, Jourdain M | [Aspect] | Yes | Closed | CCB approved to Close | Augustin, Jourdain M | Administrative Task | [Aspect] | Yes | Closed | Administrative Task Complete | Augustin, Jourdain M | [Aspect] | Design | CCB Review | Augustin, Jourdain M | CAPA Action | Closed | Closed in Error | [Aspect] | Yes | Business Rule | Administrative Task | Administrative Task | Business Rule | Augustin, Jourdain M | CAPA Action | VSTS_1537a096_c5ff_4c23_a187_872990c51753_2F-6A-0F-36-F4-ED-85-56-2C-8C-AA-CE-1E-97-9B-B1-5B-CF-64-D7 | New | 1 - Urgent - Emergency | 2 - High | 1 - Urgent - Emergency | Easy | 2 - High | 1 - Urgent - Emergency | 2 - High | Easy | Easy | 2 - High | Easy | 2 - High | Easy | 2 - High | Easy | 2 - High | Easy | 2 - High | Easy | 2 - High | Easy | 2 - High | Easy | 2 - High | 2 - High | Review New Submitted Request | 1 - Urgent - Emergency | 1 - Urgent - Emergency | 1 - Urgent - Emergency | 1 - Urgent - Emergency | 1 - Urgent - Emergency | 1 - Urgent - Emergency | 1 - Urgent - Emergency | 1 - Urgent - Emergency | 1 - Urgent - Emergency | CCB Review | Configuration Management | Configuration Management | Configuration Management | Configuration Management | Complete and Does Not Require Review/Test | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Augustin, Jourdain M | Business Analyst | Business Analyst | Business Analyst | Augustin, Jourdain M | Closed | Administrative Task not Completed
|  |  |  | \Assignment and Exception Tracking System | \Assignment and Exception\A_E 2015 | Barnes, Amy E | [Assignment and Exception] | VSTS_1537a096_c5ff_4c23_a187_872990c51753_20-B5-FF-1A-30-9C-85-1A-A5-5F-41-8C-5C-7D-57-1C-5E-01-21-9C | Proposed | Proposed | Investigate | Barnes, Amy E | Proposed | Investigate | Barnes, Amy E | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_Vangent.AIM.SecurityImpact | Proposed | Additional IA Needed | Barnes, Amy E | [Assignment and Exception] | Proposed | Acceptance tests pass | Barnes, Amy E | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_Vangent.AIM.SecurityImpact | Proposed | Assessment Cancelled | Barnes, Amy E | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_Vangent.AIM.SecurityImpact | Proposed | Closed in Error | Barnes, Amy E | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_Vangent.AIM.SecurityImpact | Hold | Awaiting Customer Response | Barnes, Amy E | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_Vangent.AIM.SecurityImpact | Proposed | CCB approved to Reject/Close | Feature | Barnes, Amy E | [Assignment and Exception] | Resolved | Accepted with Minor Changes | Barnes, Amy E | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_Vangent.AIM.SecurityImpact | Proposed | CCB approved to Reject/Close | Barnes, Amy E | Data Change | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_Vangent.AIM.SecurityImpact | Proposed | Administrative Task not Complete | Barnes, Amy E | [Assignment and Exception] | Ready | Completed | Barnes, Amy E | Change Request | Proposed | Investigate | [Assignment and Exception] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Vangent.AIM.SecurityImpact | Feature | Data Change | Data Change | Feature | Barnes, Amy E | Change Request |  | VSTS_1537a096_c5ff_4c23_a187_872990c51753_EC-00-3F-2A-1B-3A-AC-1E-94-DC-8A-0F-17-A8-F2-E7-2D-4E-26-2D | 2 - High | 3 - Medium | 2 - High | Moderate | 3 - Medium | 2 - High | 3 - Medium | Moderate | Moderate | 3 - Medium | Moderate | 3 - Medium | Moderate | 3 - Medium | Moderate | 3 - Medium | Moderate | 3 - Medium | Moderate | 3 - Medium | Moderate | 3 - Medium | Moderate | 3 - Medium | 3 - Medium | Submit Admin Task | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | 2 - High | Closed | Design Development | Development | Development | Design Development | Work Cancelled | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Barnes, Amy E | Configuration Manager | Configuration Manager | Configuration Manager | Black, Karen S | Resolved | Data Quality Checks Completed
|  |  |  | \Attendance Tracking Tool | \Assignment and Exception\A_E 2015\A_E 2015-10 | Borkowski, Steve T | [Attendance Tracking Tool] |  | Resolved | Resolved | Investigation Complete | Borkowski, Steve T | Resolved | Investigation Complete | Borkowski, Steve T | [Attendance Tracking Tool] |  | Resolved | Administrative Task Completed & Accepted | Borkowski, Steve T | [Attendance Tracking Tool] | Resolved | Accepted | Borkowski, Steve T | [Attendance Tracking Tool] |  | Resolved | Assessment Complete | Borkowski, Steve T | [Attendance Tracking Tool] |  | Resolved | Impact Assessment Complete | Borkowski, Steve T | [Attendance Tracking Tool] |  | Proposed | Build Failure | Borkowski, Steve T | [Attendance Tracking Tool] |  | Resolved | CCB Review | Functional | Borkowski, Steve T | [Attendance Tracking Tool] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Review_System.State | CCB approved to Close | Borkowski, Steve T | [Attendance Tracking Tool] |  | Resolved | CCB Review | Borkowski, Steve T | Data Quality Checks | [Attendance Tracking Tool] |  | Resolved | Administrative Task not Completed | Borkowski, Steve T | [Attendance Tracking Tool] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_System.State | Deferred | Borkowski, Steve T | Feature | Resolved | Investigation Complete | [Attendance Tracking Tool] |  | Functional | Data Quality Checks | Data Quality Checks | Functional | Borkowski, Steve T | Code Review Request |  |  | 3 - Moderate | 4 - Low | 3 - Moderate | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_Vangent.AIM.Complexity | 4 - Low | 3 - Moderate | 4 - Low | VSTS_1537a096_c5ff_4c23_a187_872990c51753_4C-7A-04-25-8D-B1-C9-60-40-74-B0-64-14-F8-05-3C-BD-3E-2C-9B | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_Vangent.AIM.Complexity | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_Vangent.AIM.Complexity | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_Vangent.AIM.Complexity | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_Vangent.AIM.Complexity | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_Vangent.AIM.Complexity | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_Vangent.AIM.Complexity | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_Vangent.AIM.Complexity | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Vangent.AIM.Complexity | 4 - Low | 4 - Low | Submit Data Quality Checks | 3 - Moderate | 3 - Moderate | 3 - Moderate | 3 - Moderate | 3 - Moderate | 3 - Moderate | 3 - Moderate | 3 - Moderate | 3 - Moderate | Meeting was Held | Development | Governance | Governance | Development | Work Not Completed. Moving Remaining Work to the Next Iteration | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Borkowski, Steve T | Customer | Customer | Customer | Borkowski, Steve T | VSTS_1537a096_c5ff_4c23_a187_872990c51753_26-FF-DE-08-0D-C9-09-53-1F-05-FD-90-D7-AD-D4-D5-FF-6A-89-45 | Dev and V&V Complete
|  |  |  | \Business Rule | \Assignment and Exception\A_E 2015\A_E 2015-11 | Clark, Bridget L | [Casework Management Tool] |  | VSTS_1537a096_c5ff_4c23_a187_872990c51753_F9-E1-2C-98-86-04-E5-7D-4B-B1-8B-C7-8F-D4-55-95-91-76-6C-DD | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA_System.State | New | Clark, Bridget L | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA Action_System.State | New | Clark, Bridget L | [Casework Management Tool] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_System.State | Administrative Task not Completed | Clark, Bridget L | [Configuration Management] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Feature_System.State | CCB approved to Close | Clark, Bridget L | [Casework Management Tool] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_System.State | Assessment Completed & Accepted | Clark, Bridget L | [Casework Management Tool] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_System.State | Investigate | Clark, Bridget L | [Casework Management Tool] |  | Resolved | Cannot Reproduce | Clark, Bridget L | [Casework Management Tool] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_System.State | Closed | Interface | Clark, Bridget L | [Configuration Management] |  | CCB Review | Clark, Bridget L | [Casework Management Tool] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_System.State | Closed in Error | Clark, Bridget L | Escalated Issue Resolution | [Casework Management Tool] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_System.State | Build & Compile Failed | Clark, Bridget L | [Casework Management Tool] |  | Duplicate | Clark, Bridget L | Impact Assessment | Hold | New | [Casework Management Tool] |  | Interface | Escalated Issue Resolution | Escalated Issue Resolution | Interface | Clark, Bridget L | Code Review Response |  |  | 4 - Low | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA_Microsoft.VSTS.Common.Severity | 4 - Low |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA Action_Microsoft.VSTS.Common.Severity | 4 - Low | VSTS_1537a096_c5ff_4c23_a187_872990c51753_45-F5-9C-27-95-2A-7B-65-33-77-4B-A9-8C-81-2F-7D-A7-A1-56-F2 |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_Microsoft.VSTS.Common.Severity |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_Microsoft.VSTS.Common.Severity |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_Microsoft.VSTS.Common.Severity |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_Microsoft.VSTS.Common.Severity |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_Microsoft.VSTS.Common.Severity |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_Microsoft.VSTS.Common.Severity |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_Microsoft.VSTS.Common.Severity |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_Microsoft.VSTS.Common.Severity | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Microsoft.VSTS.Common.Severity | Submit Dev and V&V | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | 4 - Low | Out-of-scope | Governance | Process Improvement | Process Improvement | Governance | VSTS_1537a096_c5ff_4c23_a187_872990c51753_EC-30-74-22-2D-E5-DE-76-41-6B-CC-13-43-11-0E-66-65-9E-AA-6A | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Clark, Bridget L | Operations | Operations | Operations | Coughlin, Brian E |  | Implement to Prod Complete
|  |  |  | \Casework Management Tool | \Assignment and Exception\A_E 2015\A_E 2015-12 | Coughlin, Brian E | [Configuration Management] |  |  |  | Overtaken by events | Coughlin, Brian E |  | Overtaken by events | Coughlin, Brian E | [Configuration Management] |  |  | CCB approved to Close | Coughlin, Brian E | [Disenrollment] |  | CCB approved to Reject/Close | Coughlin, Brian E | [Configuration Management] |  |  | CCB approved to Reject/Close | Coughlin, Brian E | [Configuration Management] |  |  | Investigation Complete | Coughlin, Brian E | [Configuration Management] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_System.State | CCB approved to Reject and Close | Coughlin, Brian E | [Configuration Management] |  |  | Closed in Error | Operational | Coughlin, Brian E | [Desktop] |  | Closed in Error | Coughlin, Brian E | [Configuration Management] |  |  | Eliminated | Coughlin, Brian E | Meeting | [Configuration Management] |  |  | Build & Compile Passed | Coughlin, Brian E | [Configuration Management] |  | New | Coughlin, Brian E | Issue | Design | Overtaken by events | [Configuration Management] |  | Operational | Meeting | Meeting | Operational | Coughlin, Brian E | Feature |  |  | 5 - Hold |  | 5 - Hold |  |  | 5 - Hold | [19 empty] | Submit Implementation | 5 - Hold | 5 - Hold | 5 - Hold | 5 - Hold | 5 - Hold | 5 - Hold | 5 - Hold | 5 - Hold | 5 - Hold | Split | Process Improvement | Project Management | Project Management | Process Improvement |  | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Coughlin, Brian E | Program Manager | Program Manager | Program Manager | Dye, Ellen |  | Post Prod V&V Complete
|  |  |  | \eCoaching Log | \Assignment and Exception\A_E 2016 | Dye, Ellen | [Disenrollment] |  |  |  | Rejected (not an issue) | Dye, Ellen |  | Rejected (not an issue) | Dye, Ellen | [Disenrollment] |  |  | CCB approved to Reject/Close | Dye, Ellen | [eCoaching] |  | CCB Review | Dye, Ellen | [Disenrollment] |  |  | CCB Review | Dye, Ellen | [Disenrollment] |  |  | Not Implemented | Dye, Ellen | [Disenrollment] |  |  | CCB approved to Reject/Close | Dye, Ellen | [Disenrollment] |  |  | Code Complete - Test Passed - In BETA Test | Program Meeting | Dye, Ellen | [Disenrollment] |  | Major Changes Complete | Dye, Ellen | [Disenrollment] |  |  | Mitigated | Dye, Ellen | Password Change Request | [Disenrollment] |  |  | CCB Review | Dye, Ellen | [Disenrollment] |  | Obsolete | Dye, Ellen | Problem Report | Ready | Rejected (not an issue) | [Disenrollment] |  | Program Meeting | Password Change Request | Password Change Request | Program Meeting | Dye, Ellen | Feedback Request |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_Vangent.AIM.RMPriority |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Vangent.AIM.RMPriority |  |  | VSTS_1537a096_c5ff_4c23_a187_872990c51753_22-66-F5-4B-F5-46-6D-EE-3F-C6-5A-48-92-72-E5-9C-EB-CD-9F-2A | [19 empty] | Submit Meeting Task | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_Vangent.AIM.CMPriority | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Feature_Vangent.AIM.CMPriority | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_Vangent.AIM.CMPriority | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_Vangent.AIM.CMPriority | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_Vangent.AIM.CMPriority | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_Vangent.AIM.CMPriority | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_Vangent.AIM.CMPriority | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_Vangent.AIM.CMPriority | 2 - High | VSTS_1537a096_c5ff_4c23_a187_872990c51753_66-4A-67-2B-1C-02-C1-E2-04-32-55-44-A6-E7-5B-60-FF-F0-A4-E0 | Release Management | Release Management | Release Management | Release Management |  | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Dye, Ellen | Quality | Quality | Quality | Erickson, William T |  | Research Task Completed
|  |  |  | \Exclusion Super User Group Team | \Assignment and Exception\A_E 2016\A_E 2016-01 | Erickson, William T | [eCoaching] |  |  |  | Re-occurred | Erickson, William T |  | Re-occurred | Erickson, William T | [eCoaching] |  |  | CCB Review | Erickson, William T | [HTKR] |  | Closed in Error | Erickson, William T | [eCoaching] |  |  | Closed in Error | Erickson, William T | [eCoaching] |  |  | On Hold | Erickson, William T | [eCoaching] |  |  | CCB Review | Erickson, William T | [eCoaching] |  |  | Code Complete - Test Passed - In Customer Acceptance Test | Security | Erickson, William T | [eCoaching] |  | Minor Changes Complete | Erickson, William T | [eCoaching] |  |  | Mitigation Action Complete | Erickson, William T | Peer Review | [eCoaching] |  |  | Closed in Error | Erickson, William T | [eCoaching] |  | Reactivated | Erickson, William T | Requirement | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_System.State | Re-occurred | [eCoaching] |  | Security | Peer Review | Peer Review | Security | Erickson, William T | Feedback Response | [27 empty] | Submit Planned Operational Activity | [8 empty] | 5 - Hold |  | Requirements | Requirements | Requirements | Requirements |  | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Erickson, William T | Software Engineer | Software Engineer | Software Engineer | Gilman, Joseph R |  | Server Maintenance Complete
|  |  |  | \Functional | \Assignment and Exception\A_E 2016\A_E 2016-02 | Foster, Mark S | [HTKR] |  |  |  | Re-opened | Foster, Mark S |  | Re-opened | Foster, Mark S | [HTKR] |  |  | Closed in Error | Foster, Mark S | [Outbound Analysis and Reporting] |  | Investigate | Foster, Mark S | [HTKR] |  |  | Deferred | Foster, Mark S | [HTKR] |  |  | Pending Dev and V&V | Foster, Mark S | [HTKR] |  |  | Closed in Error | Foster, Mark S | [HTKR] |  |  | Code Complete and Testing Passed | Software | Foster, Mark S | [HTKR] |  | New | Foster, Mark S | [HTKR] |  |  | Mitigation Action Unsatisfactory (rework) | Foster, Mark S | Research | [HTKR] |  |  | Code Review Complete. Ready for Build & Compile | Foster, Mark S | [HTKR] |  | Update Test Case | Foster, Mark S | Review |  | Re-opened | [HTKR] |  | Software | Research | Research | Software | Foster, Mark S | Impact Assessment | [27 empty] | Submit Server Maintenance | [8 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Vangent.AIM.CMPriority |  | Security | Security | Security | Security |  | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Foster, Mark S | Software Project Manager | Software Project Manager | Software Project Manager | Haltmeyer, Jacqueline K |  | V&V Complete
|  |  |  | \Interface | \Assignment and Exception\A_E 2016\A_E 2016-03 | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  |  |  | Resolution Verified and Accepted | Haltmeyer, Jacqueline K |  | Resolution Verified and Accepted | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  |  | Code Complete and System Tested | Haltmeyer, Jacqueline K | [Performance Management] |  | Investigation Complete | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  |  | Duplicate | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  |  | Pending IA | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  |  | Customer Postponed | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  |  | Implemented to Production | System Compliance | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  | On Hold | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  |  | Mitigation Triggered | Haltmeyer, Jacqueline K | Weekly Build | [Outbound Analysis and Reporting] |  |  | Code Review Failed | Haltmeyer, Jacqueline K | [Outbound Analysis and Reporting] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_System.Reason | Haltmeyer, Jacqueline K | Risk |  | Resolution Verified and Accepted | [Outbound Analysis and Reporting] |  | System Compliance | Weekly Build | Weekly Build | System Compliance | Haltmeyer, Jacqueline K | Issue | [27 empty] | Submit V&V | [10 empty] | Test | Supplier Agreement Management | Supplier Agreement Management | Test |  | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Haltmeyer, Jacqueline K | Support Staff | Support Staff | Support Staff | Hinman, David L |  | Work Not Completed. Moving Remaining Work to the Next Iteration
|  |  |  | \Outbound Analysis and Reporting | \Assignment and Exception\A_E 2016\A_E 2016-04 | Harrison-Hosford, Holly L | [Performance Management] |  |  |  | Resolved | Harrison-Hosford, Holly L |  | Resolved | Harrison-Hosford, Holly L | [Performance Management] |  |  | Documentation updates are complete & verified | Harrison-Hosford, Holly L | [Quality Data Mart] |  | New | Harrison-Hosford, Holly L | [Performance Management] |  |  | Investigate | Harrison-Hosford, Holly L | [Performance Management] |  |  | Pending Implementation | Harrison-Hosford, Holly L | [Performance Management] |  |  | Deferred | Harrison-Hosford, Holly L | [Performance Management] |  |  | Investigate | System Constraint | Harrison-Hosford, Holly L | [Performance Management] |  | Removing from hold to complete the work | Harrison-Hosford, Holly L | [Performance Management] |  |  | New | Harrison-Hosford, Holly L | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_Vangent.HSES.RequestType | [Performance Management] |  |  | Complete and Does Not Require Review/Test | Harrison-Hosford, Holly L | [Performance Management] |  |  | Harrison-Hosford, Holly L | Task |  | Resolved | [Performance Management] |  | System Constraint | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Vangent.HSES.RequestType | VSTS_1537a096_c5ff_4c23_a187_872990c51753_F6-05-0A-CE-E4-BA-20-C4-39-81-44-23-96-60-6E-13-0E-6C-DC-0A | System Constraint | Harrison-Hosford, Holly L | Problem Report | [27 empty] | VSTS_1537a096_c5ff_4c23_a187_872990c51753_D6-B0-01-FC-C8-1E-D8-87-7A-2C-17-B9-E2-8A-3A-5E-C6-D9-E9-5F | [10 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_Microsoft.VSTS.Common.Discipline | Test | Test | Project Management |  | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Harrison-Hosford, Holly L | Test Engineer | Test Engineer | Test Engineer | Huang, Lili |  | Work Rejected/Cancelled
|  |  |  | \Performance Management | \Assignment and Exception\A_E 2016\A_E 2016-05 | Herber, Gary S | [Quality] |  |  |  | Rework | Herber, Gary S |  | Rework | Herber, Gary S | [Quality] |  |  | Documentation updates complete & reviewed | Herber, Gary S | [Quality] |  | On Hold | Herber, Gary S | [Quality] |  |  | New | Herber, Gary S | [Quality] |  |  | Pending Verification and Validation | Herber, Gary S | [Quality] |  |  | Duplicate | Herber, Gary S | [Quality] |  |  | Investigation Complete | System Documentation | Herber, Gary S | [Quality Data Mart] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Review_System.Reason | Herber, Gary S | [Quality] |  |  | On Hold | Herber, Gary S |  | [Quality] |  |  | Data Quality Checks Completed | Herber, Gary S | [Quality] |  |  | Herber, Gary S | Test Case |  | Rework | [Quality] |  | System Documentation |  |  | System Documentation | Herber, Gary S | Requirement | [39 empty] | Training | Training | Supplier Agreement Management |  | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | Herber, Gary S | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_Vangent.HSES.SourceOfRequest | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Vangent.HSES.SourceOfRequest | VSTS_1537a096_c5ff_4c23_a187_872990c51753_73-C1-54-C0-71-0A-2E-77-4E-BA-9B-B7-6E-64-A2-B7-3F-5E-C2-D5 | Hutson, James E |  | VSTS_1537a096_c5ff_4c23_a187_872990c51753_41-FF-46-CF-9E-A2-7E-79-F5-E9-DA-A7-AB-72-28-62-9D-80-F4-08
|  |  |  | \Quality | \Assignment and Exception\A_E 2016\A_E 2016-06 | Hinman, David L | [Report Automation] |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA_System.Reason | Hinman, David L |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA Action_System.Reason | Hinman, David L | [Report Automation] |  |  | Investigate | Hinman, David L | [Telecom] |  | Out-of-scope | Hinman, David L | [Report Automation] |  |  | Not complete | Hinman, David L | [Report Automation] |  |  | Post Prod V&V Failed | Hinman, David L | [Report Automation] |  |  | Fixed | Hinman, David L | [Report Automation] |  |  | Meeting was Held | System Qualities | Hinman, David L | [Quality] |  |  | Hinman, David L | [Report Automation] |  |  | Overtaken by events | Hinman, David L |  | [Report Automation] |  |  | Dev and V&V Complete | Hinman, David L | [Report Automation] |  |  | Hinman, David L | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_System.WorkItemType |  | Abandoned | [Report Automation] |  | System Qualities |  |  | System Qualities | Hinman, David L | Review | [39 empty] | VSTS_1537a096_c5ff_4c23_a187_872990c51753_35-3E-3B-6A-4C-D8-B2-37-F3-6F-32-66-30-13-8F-58-4D-DA-31-C4 | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_Microsoft.VSTS.Common.Discipline | Training |  | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L | Hinman, David L |  |  |  | Ingram, Michael T
|  |  |  | \Security | \Assignment and Exception\A_E 2016\A_E 2016-07 | Huang, Lili | [Telecom] |  |  |  |  | Huang, Lili |  |  | Huang, Lili | [Telecom] |  |  | Investigation Complete | Huang, Lili | [Written Correspondence_Scanning] |  | Postponed | Huang, Lili | [Telecom] |  |  | On Hold | Huang, Lili | [Telecom] |  |  | Post Prod V&V Passed | Huang, Lili | [Scorecard] |  |  | Generated PR | Huang, Lili | [Telecom] |  |  | New | Team Meeting | Huang, Lili | [Scorecard] |  |  | Huang, Lili | [Telecom] |  |  | Rejected | Huang, Lili |  | [Telecom] |  |  | Dev Complete. Ready for Build & Compile | Huang, Lili | [Telecom] |  |  | Huang, Lili |  |  | Additional IA Needed | [Telecom] |  | Team Meeting |  |  | Team Meeting | Huang, Lili | Risk | [41 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Microsoft.VSTS.Common.Discipline |  | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili | Huang, Lili |  |  |  | Keune, Leslie A
|  |  |  | \Telecom | \Assignment and Exception\A_E 2016\A_E 2016-08 | Hutson, James E | [Written Correspondence_Scanning] |  |  |  |  | Hutson, James E |  |  | Hutson, James E | [Written Correspondence_Scanning] |  |  | Not Implemented | Hutson, James E | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Feature_Vangent.AIM.FunctionalArea |  | Reintroduced in Scope | Hutson, James E | [Written Correspondence_Scanning] |  |  | Provide Impact Assessment | Hutson, James E | [Written Correspondence_Scanning] |  |  | Post Prod Verification Completed | Hutson, James E | [Telecom] |  |  | Generated RQMT | Hutson, James E | [Written Correspondence_Scanning] |  |  | On Hold | Technical | Hutson, James E | [Telecom] |  |  | Hutson, James E | [Written Correspondence_Scanning] |  |  | Removing from hold to complete the work | Hutson, James E |  | [Written Correspondence_Scanning] |  |  | Dev Complete. Ready for Code Review | Hutson, James E | [Written Correspondence_Scanning] |  |  | Hutson, James E |  |  | Administrative Task Completed & Accepted | [Written Correspondence_Scanning] |  | Technical |  |  | Technical | Hutson, James E | Shared Parameter | [43 empty] | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E | Hutson, James E |  |  |  | Miller, Jackie K
|  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_System.AreaPath | \Assignment and Exception\A_E 2016\A_E 2016-09 | Ingram, Michael T | VSTS_1537a096_c5ff_4c23_a187_872990c51753_12-8B-68-D6-3F-FF-6F-04-83-8F-6C-F9-52-28-42-EE-CD-4E-37-C7 |  |  |  |  | Ingram, Michael T |  |  | Ingram, Michael T | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_Vangent.AIM.FunctionalArea |  |  | On Hold | Ingram, Michael T |  |  | Rejected | Ingram, Michael T | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_Vangent.AIM.FunctionalArea |  |  | Rejected | Ingram, Michael T | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_Vangent.AIM.FunctionalArea |  |  | Post Production Verification | Ingram, Michael T | [Written Correspondence_Scanning] |  |  | Implement to Prod Complete | Ingram, Michael T | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_Vangent.AIM.FunctionalArea |  |  | Out-of-scope | Training | Ingram, Michael T | [Written Correspondence_Scanning] |  |  | Ingram, Michael T | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_Vangent.AIM.FunctionalArea |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_System.Reason | Ingram, Michael T |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_Vangent.AIM.FunctionalArea |  |  | Dev Server V&V | Ingram, Michael T | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_Vangent.AIM.FunctionalArea |  |  | Ingram, Michael T |  |  | Administrative Task not Completed | [Quality Data Mart] |  | Training |  |  | Training | Ingram, Michael T | Shared Steps | [43 empty] | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T | Ingram, Michael T |  |  |  | Mishra, Lex S
[5 empty] | \Assignment and Exception\A_E 2016\A_E 2016-10 | Keune, Leslie A | [5 empty] | Keune, Leslie A |  |  | Keune, Leslie A |  |  |  | Out-of-scope | Keune, Leslie A |  |  | Removing from hold to complete the work | Keune, Leslie A |  |  |  | Removing from hold to complete the work | Keune, Leslie A |  |  |  | Rejected | Keune, Leslie A | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_Vangent.AIM.FunctionalArea |  |  | Investigate | Keune, Leslie A |  |  |  | Postponed | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_Microsoft.VSTS.CMMI.RequirementType | Keune, Leslie A | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Review_Vangent.AIM.FunctionalArea |  |  | Keune, Leslie A |  |  |  |  | Keune, Leslie A |  |  |  |  | Implement to Prod Complete | Keune, Leslie A |  |  |  | Keune, Leslie A |  |  | CCB approved to Close | [Scorecard] |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Microsoft.VSTS.CMMI.RequirementType |  |  | VSTS_1537a096_c5ff_4c23_a187_872990c51753_0E-A6-C7-9D-DB-21-57-9F-E0-AB-4C-D7-8B-95-14-87-FE-39-21-45 | Keune, Leslie A | Task | [43 empty] | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A | Keune, Leslie A |  |  |  | Moharar, Kalyan
[5 empty] | \Assignment and Exception\A_E 2016\A_E 2016-11 | Miller, Jackie K | [5 empty] | Miller, Jackie K |  |  | Miller, Jackie K |  |  |  | Pending Dev and V&V | Miller, Jackie K |  |  | Requirements complete | Miller, Jackie K |  |  |  | Server Maintenance Assessment Completed & Accepted | Miller, Jackie K |  |  |  | Rejected (not an issue) | Miller, Jackie K |  |  |  | Investigation Complete | Miller, Jackie K |  |  |  | Reintroduced in Scope |  | Miller, Jackie K |  |  |  | Miller, Jackie K |  |  |  |  | Miller, Jackie K |  |  |  |  | Intregration Test Complete | Miller, Jackie K |  |  |  | Miller, Jackie K |  |  | CCB approved to Reject/Close | [Desktop] | [5 empty] | Miller, Jackie K | Test Case | [43 empty] | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K | Miller, Jackie K |  |  |  | Palacherla, Susmitha C
[5 empty] | \Assignment and Exception\A_E 2016-12 | Mishra, Lex S | [5 empty] | Mishra, Lex S |  |  | Mishra, Lex S |  |  |  | Pending IA | Mishra, Lex S |  |  | Research complete | Mishra, Lex S |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_System.Reason | Mishra, Lex S |  |  |  | Removing from hold to complete the work | Mishra, Lex S |  |  |  | Monitoring in Field | Mishra, Lex S |  |  |  | Rejected |  | Mishra, Lex S |  |  |  | Mishra, Lex S |  |  |  |  | Mishra, Lex S |  |  |  |  | Investigate | Mishra, Lex S |  |  |  | Mishra, Lex S |  |  | CCB Review | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Vangent.AIM.FunctionalArea | [5 empty] | Mishra, Lex S | Test Plan | [43 empty] | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S | Mishra, Lex S |  |  |  | Pemberton, Brian R
[5 empty] | \Assignment and Exception\A_E 2017-01 | Moharar, Kalyan | [5 empty] | Moharar, Kalyan |  |  | Moharar, Kalyan |  |  |  | Pending Implementation | Moharar, Kalyan |  |  | Research Completed and Ready to Close | Moharar, Kalyan |  |  |  |  | Moharar, Kalyan |  |  |  | Re-occurred | Moharar, Kalyan |  |  |  | Monitoring in the field | Moharar, Kalyan |  |  |  | Removing from hold to complete the work |  | Moharar, Kalyan |  |  |  | Moharar, Kalyan |  |  |  |  | Moharar, Kalyan |  |  |  |  | Investigation Complete | Moharar, Kalyan |  |  |  | Moharar, Kalyan |  |  | Code Complete and System Tested | [6 empty] | Moharar, Kalyan | Test Suite | [43 empty] | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan | Moharar, Kalyan |  |  |  | Queen, Timothy K
[5 empty] | \Assignment and Exception\A_E 2017-02 | Palacherla, Susmitha C | [5 empty] | Palacherla, Susmitha C |  |  | Palacherla, Susmitha C |  |  |  | Pending Server Maintenance | Palacherla, Susmitha C |  |  | Split | Palacherla, Susmitha C |  |  |  |  | Palacherla, Susmitha C |  |  |  | Re-opened | Palacherla, Susmitha C |  |  |  | Not fixed | Palacherla, Susmitha C |  |  |  | Split |  | Palacherla, Susmitha C |  |  |  | Palacherla, Susmitha C |  |  |  |  | Palacherla, Susmitha C |  |  |  |  | On Hold | Palacherla, Susmitha C |  |  |  | Palacherla, Susmitha C |  |  | Documentation updates are complete & verified | [6 empty] | Palacherla, Susmitha C | VSTS_1537a096_c5ff_4c23_a187_872990c51753_B3-00-B1-36-C3-C1-EB-46-6C-DD-E2-CD-1F-71-10-7A-A7-0C-14-2C | [43 empty] | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C | Palacherla, Susmitha C |  |  |  | Reem, James P
[5 empty] | \Attendance Tracking Tool | Pemberton, Brian R | [5 empty] | Pemberton, Brian R |  |  | Pemberton, Brian R |  |  |  | Pending Verification and Validation | Pemberton, Brian R |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Feature_System.Reason | Pemberton, Brian R |  |  |  |  | Pemberton, Brian R |  |  |  | Resolution Verified and Accepted | Pemberton, Brian R |  |  |  | Obsolete | Pemberton, Brian R |  |  |  | Task Completed/Close |  | Pemberton, Brian R |  |  |  | Pemberton, Brian R |  |  |  |  | Pemberton, Brian R |  |  |  |  | Pending Admin Task | Pemberton, Brian R |  |  |  | Pemberton, Brian R |  |  | Documentation updates complete & reviewed | [6 empty] | Pemberton, Brian R | [44 empty] | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R | Pemberton, Brian R |  |  |  | Shown, James B
[5 empty] | \Attendance Tracking Tool\ATT 2015 | Queen, Timothy K | [5 empty] | Queen, Timothy K |  |  | Queen, Timothy K |  |  |  | Post Prod V&V Failed | Queen, Timothy K |  |  |  | Queen, Timothy K |  |  |  |  | Queen, Timothy K |  |  |  | Resolved | Queen, Timothy K |  |  |  | On Hold | Queen, Timothy K |  |  |  | Validation Test Failed |  | Queen, Timothy K |  |  |  | Queen, Timothy K |  |  |  |  | Queen, Timothy K |  |  |  |  | Pending Data Quality Checks | Queen, Timothy K |  |  |  | Queen, Timothy K |  |  | Not Implemented | [6 empty] | Queen, Timothy K | [44 empty] | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K | Queen, Timothy K |  |  |  | Stearns, Douglas R
[5 empty] | \Attendance Tracking Tool\ATT 2015\ATT 2015-10 | Reem, James P | [5 empty] | Reem, James P |  |  | Reem, James P |  |  |  | Post Prod V&V Passed | Reem, James P |  |  |  | Reem, James P |  |  |  |  | Reem, James P |  |  |  | Review New Submitted Request | Reem, James P |  |  |  | Pending customer direction | Reem, James P |  |  |  | Validation Test Passed |  | Reem, James P |  |  |  | Reem, James P |  |  |  |  | Reem, James P |  |  |  |  | Pending Development | Reem, James P |  |  |  | Reem, James P |  |  | On Hold | [6 empty] | Reem, James P | [44 empty] | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P | Reem, James P |  |  |  | Stein, Lisa D
[5 empty] | \Attendance Tracking Tool\ATT 2015\ATT 2015-11 | Shown, James B | [5 empty] | Shown, James B |  |  | Shown, James B |  |  |  | Post Prod Verification Completed | Shown, James B |  |  |  | Shown, James B |  |  |  |  | Shown, James B |  |  |  | Rework | Shown, James B |  |  |  | Pending Dev & V&V | Shown, James B |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_System.Reason |  | Shown, James B |  |  |  | Shown, James B |  |  |  |  | Shown, James B |  |  |  |  | Pending Implementation | Shown, James B |  |  |  | Shown, James B |  |  | Out-of-scope | [6 empty] | Shown, James B | [44 empty] | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B | Shown, James B |  |  |  | Szabo, Brian P
[5 empty] | \Attendance Tracking Tool\ATT 2015\ATT 2015-12 | Siracusa, Michael A | [5 empty] | Siracusa, Michael A |  |  | Siracusa, Michael A |  |  |  | Post Production Verification | Siracusa, Michael A |  |  |  | Siracusa, Michael A |  |  |  |  | Siracusa, Michael A |  |  |  | Updating to detail the appropriate Reason | Siracusa, Michael A |  |  |  | Pending Implementation | Siracusa, Michael A | [5 empty] | Siracusa, Michael A |  |  |  | Siracusa, Michael A |  |  |  |  | Siracusa, Michael A |  |  |  |  | Pending Planned Operational Activity | Siracusa, Michael A |  |  |  | Siracusa, Michael A |  |  | Pending Dev and V&V | [6 empty] | Siracusa, Michael A | [44 empty] | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A | Siracusa, Michael A |  |  |  | Treinen, Lola R
[5 empty] | \Attendance Tracking Tool\ATT 2016 | Stearns, Douglas R | [5 empty] | Stearns, Douglas R |  |  | Stearns, Douglas R |  |  |  | Rejected | Stearns, Douglas R |  |  |  | Stearns, Douglas R |  |  |  |  | Stearns, Douglas R |  |  |  | V&V Passed | Stearns, Douglas R |  |  |  | Pending Verification and Validation | Stearns, Douglas R | [5 empty] | Stearns, Douglas R |  |  |  | Stearns, Douglas R |  |  |  |  | Stearns, Douglas R |  |  |  |  | Pending Server Maintenance | Stearns, Douglas R |  |  |  | Stearns, Douglas R |  |  | Pending IA | [6 empty] | Stearns, Douglas R | [44 empty] | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R | Stearns, Douglas R |  |  |  | VSTS_1537a096_c5ff_4c23_a187_872990c51753_C8-2A-0B-0C-74-2F-83-66-DD-CF-90-6F-A5-23-5B-FE-6A-69-BD-E6
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-01 | Stein, Lisa D | [5 empty] | Stein, Lisa D |  |  | Stein, Lisa D |  |  |  | Rejected/Work Cancelled | Stein, Lisa D |  |  |  | Stein, Lisa D |  |  |  |  | Stein, Lisa D |  |  |  | Validation Test Failed | Stein, Lisa D |  |  |  | Post Prod V&V Completed | Stein, Lisa D | [5 empty] | Stein, Lisa D |  |  |  | Stein, Lisa D |  |  |  |  | Stein, Lisa D |  |  |  |  | Pending Team Meeting | Stein, Lisa D |  |  |  | Stein, Lisa D |  |  | Pending Implementation | [6 empty] | Stein, Lisa D | [44 empty] | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D | Stein, Lisa D
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-02 | Szabo, Brian P | [5 empty] | Szabo, Brian P |  |  | Szabo, Brian P |  |  |  | Removing from hold to complete the work | Szabo, Brian P |  |  |  | Szabo, Brian P |  |  |  |  | Szabo, Brian P |  |  |  | Verification and Validation | Szabo, Brian P |  |  |  | Post Prod V&V Failed | Szabo, Brian P | [5 empty] | Szabo, Brian P |  |  |  | Szabo, Brian P |  |  |  |  | Szabo, Brian P |  |  |  |  | Pending Verification and Validation | Szabo, Brian P |  |  |  | Szabo, Brian P |  |  | Pending Server Maintenance | [6 empty] | Szabo, Brian P | [44 empty] | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P | Szabo, Brian P
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-03 | Tiongson, John Eric Z (NONUS) | [5 empty] | Tiongson, John Eric Z (NONUS) |  |  | Tiongson, John Eric Z (NONUS) |  |  |  | Review New Submitted Request | Tiongson, John Eric Z (NONUS) |  |  |  | Tiongson, John Eric Z (NONUS) |  |  |  |  | Tiongson, John Eric Z (NONUS) |  |  |  | Waiting on Dev and V&V | Tiongson, John Eric Z (NONUS) |  |  |  | Post Prod V&V Passed | Tiongson, John Eric Z (NONUS) | [5 empty] | Tiongson, John Eric Z (NONUS) |  |  |  | Tiongson, John Eric Z (NONUS) |  |  |  |  | Tiongson, John Eric Z (NONUS) |  |  |  |  | Performance Test Complete | Tiongson, John Eric Z (NONUS) |  |  |  | Tiongson, John Eric Z (NONUS) |  |  | Pending Verification and Validation | [6 empty] | Tiongson, John Eric Z (NONUS) | [44 empty] | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS) | Tiongson, John Eric Z (NONUS)
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-04 | Treinen, Lola R | [5 empty] | Treinen, Lola R |  |  | Treinen, Lola R |  |  |  | Server Maintenance Complete | Treinen, Lola R |  |  |  | Treinen, Lola R |  |  |  |  | Treinen, Lola R |  |  |  | Waiting on Split Dev and V&V | Treinen, Lola R |  |  |  | Regression | Treinen, Lola R | [5 empty] | Treinen, Lola R |  |  |  | Treinen, Lola R |  |  |  |  | Treinen, Lola R |  |  |  |  | Post Prod V&V | Treinen, Lola R |  |  |  | Treinen, Lola R |  |  | Post Prod V&V Failed | [6 empty] | Treinen, Lola R | [44 empty] | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R | Treinen, Lola R
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-05 | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA_System.CreatedBy | [5 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA Action_System.CreatedBy |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_System.CreatedBy |  |  |  | Updating to detail the appropriate Reason | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Feature_System.CreatedBy |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_System.CreatedBy |  |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_System.CreatedBy |  |  |  | Waiting on Split IA | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_System.CreatedBy |  |  |  | Rejected | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_System.CreatedBy | [5 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Review_System.CreatedBy |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_System.CreatedBy |  |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_System.CreatedBy |  |  |  |  | Post Prod V&V Complete | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_System.CreatedBy |  |  |  | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_System.CreatedBy |  |  | Post Prod V&V Passed | [6 empty] | VSTS_1537a096_c5ff_4c23_a187_872990c51753_11-8B-A2-54-5D-C8-C3-A1-E4-FE-25-2E-75-04-B6-4C-68-9F-C7-27 | [44 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_CAPA Action_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Feature_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Impact Assessment_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Requirement_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Review_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Risk_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Test Case_System.AssignedTo | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_System.AssignedTo
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-06 | [13 empty] | V&V Passed | [13 empty] | Waiting on Split IAs |  |  |  |  | Removing from hold to complete the work | [20 empty] | Production Server V&V | [7 empty] | Post Prod Verification Completed
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-07 | [13 empty] | Validation Test Failed | [13 empty] | Waiting on Split Implementation |  |  |  |  | Review New Submitted Request | [20 empty] | Production Server V&V Failed | [7 empty] | Post Production Verification
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-08 | [13 empty] | Verification and Validation | [13 empty] | Waiting on Split V&V |  |  |  |  | Test Failed | [20 empty] | Production Server V&V to be Completed | [7 empty] | Rejected
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-09 | [13 empty] | Waiting on Dev and V&V | [13 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Issue_System.Reason |  |  |  |  | Verified | [20 empty] | QA Server V&V | [7 empty] | Rejected/Work Cancelled
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-10 | [13 empty] | Waiting on Split Dev and V&V | [18 empty] | Waiting Customer Feedback | [20 empty] | QA Server V&V Failed | [7 empty] | Removing from hold to complete the work
[5 empty] | \Attendance Tracking Tool\ATT 2016\ATT 2016-11 | [13 empty] | Waiting on Split IA | [18 empty] | Waiting for external entity to complete work | [20 empty] | Reactivated | [7 empty] | Review New Submitted Request
[5 empty] | \Attendance Tracking Tool\ATT 2016-12 | [13 empty] | Waiting on Split IA Server Maintenance | [18 empty] | Waiting on Split Dev and V&V | [20 empty] | Regression Test Complete | [7 empty] | Server Maintenance Complete
[5 empty] | \Attendance Tracking Tool\ATT 2017-01 | [13 empty] | Waiting on Split Implementation | [18 empty] | Waiting on Split IAs | [20 empty] | Rejected/Work Cancelled | [7 empty] | Updating to detail the appropriate Reason
[5 empty] | \Attendance Tracking Tool\ATT 2017-02 | [13 empty] | Waiting on Split Server Maintenance | [18 empty] | Waiting on Split Implementation | [20 empty] | Removing from hold to complete the work | [7 empty] | V&V Passed
[5 empty] | \Attendance Tracking Tool\ATT 2017-03 | [13 empty] | Waiting on Split V&V | [18 empty] | Work completed | [20 empty] | Research Task Completed | [7 empty] | Validation Test Failed
[5 empty] | \Attendance Tracking Tool\ATT 2017-04 | [13 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Change Request_System.Reason | [18 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Problem Report_System.Reason | [20 empty] | Review New Submitted Request | [7 empty] | Verification and Validation
[5 empty] | \Attendance Tracking Tool\ATT 2017-05 | [53 empty] | Server Maintenance Complete | [7 empty] | Waiting on Dev and V&V
[5 empty] | \Attendance Tracking Tool\ATT Backlog | [53 empty] | Submit Admin Task | [7 empty] | Waiting on Split Dev and V&V
[5 empty] | \Backlog | [53 empty] | Submit Data Quality Checks | [7 empty] | Waiting on Split IA
[5 empty] | \Casework Management Tool | [53 empty] | Submit Dev and V&V | [7 empty] | Waiting on Split IA Server Maintenance
[5 empty] | \Casework Management Tool\CMT 2016-11 | [53 empty] | Submit Implementation | [7 empty] | Waiting on Split Implementation
[5 empty] | \Casework Management Tool\CMT 2016-12 | [53 empty] | Submit Meeting Task | [7 empty] | Waiting on Split Server Maintenance
[5 empty] | \Casework Management Tool\CMT 2017-01 | [53 empty] | Submit Planned Operational Activity | [7 empty] | Waiting on Split V&V
[5 empty] | \Casework Management Tool\CMT 2017-02 | [53 empty] | Submit Server Maintenance | [7 empty] | Acceptance tests fail
[5 empty] | \Casework Management Tool\CMT 2017-03 | [53 empty] | Submit V&V | [7 empty] | Acceptance tests pass
[5 empty] | \Casework Management Tool\CMT 2017-04 | [53 empty] | System Test Complete | [7 empty] | Postponed
[5 empty] | \Casework Management Tool\CMT 2017-05 | [53 empty] | Unit Test Complete | [7 empty] | Reintroduced in Scope
[5 empty] | \Casework Management Tool\CMT Backlog | [53 empty] | Updating to detail the appropriate Reason | [7 empty] | Requirements complete
[5 empty] | \eCoaching Log | [53 empty] | User Acceptance Test Complete | [7 empty] | Research complete
[5 empty] | \eCoaching Log\eCL 2015 | [53 empty] | V&V Complete | [7 empty] | Research Completed and Ready to Close
[5 empty] | \eCoaching Log\eCL 2015\eCL 2015-10 | [53 empty] | Verification and Validation | [7 empty] | Split
[5 empty] | \eCoaching Log\eCL 2015\eCL 2015-11 | [53 empty] | Verification and Validation Failed | [7 empty] | Additional Assessment requested
[5 empty] | \eCoaching Log\eCL 2015\eCL 2015-12 | [53 empty] | Work Cancelled | [7 empty] | Approved
[5 empty] | \eCoaching Log\eCL 2016 | [53 empty] | Work Not Completed. Moving Remaining Work to the Next Iteration | [7 empty] | Assessment Cancelled
[5 empty] | \eCoaching Log\eCL 2016\eCL 2016-01 | [53 empty] | Work Rejected/Cancelled | [7 empty] | Assessment Complete
[5 empty] | \eCoaching Log\eCL 2016\eCL 2016-02 | [53 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_Task_System.Reason | [7 empty] | Assessment Completed & Accepted
[5 empty] | \eCoaching Log\eCL 2016\eCL 2016-03 | [61 empty] | Deferred
[5 empty] | \eCoaching Log\eCL 2016\eCL 2016-04 | [61 empty] | Duplicate
[5 empty] | \eCoaching Log\eCL 2016\eCL 2016-05 | [61 empty] | Not complete
[5 empty] | \eCoaching Log\eCL 2016\eCL Q1 | [61 empty] | Provide Impact Assessment
[5 empty] | \eCoaching Log\eCL 2016\eCL Q2 | [61 empty] | Server Maintenance Assessment Completed & Accepted
[5 empty] | \eCoaching Log\eCL Backlog | [61 empty] | Impact Assessment Complete
[5 empty] | \eCoaching Log\eCL Q3 | [61 empty] | Waiting on Split IAs
[5 empty] | \eCoaching Log\eCL Q4 | [61 empty] | As Designed
[5 empty] | \Iteration 1 | [61 empty] | Awaiting Customer Response
[5 empty] | \New Project Startup | [61 empty] | Build Failure
[5 empty] | \Outbound Analysis and Reporting | [61 empty] | Cannot Reproduce
[5 empty] | \Outbound Analysis and Reporting\OAR 2015-10 | [61 empty] | CCB approved to Reject and Close
[5 empty] | \Outbound Analysis and Reporting\OAR 2015-11 | [61 empty] | Customer Postponed
[5 empty] | \Outbound Analysis and Reporting\OAR 2015-12 | [61 empty] | Fixed
[5 empty] | \Outbound Analysis and Reporting\OAR 2016-01 | [61 empty] | Generated PR
[5 empty] | \Outbound Analysis and Reporting\OAR 2016-02 | [61 empty] | Generated RQMT
[5 empty] | \Outbound Analysis and Reporting\OAR 2016-03 | [61 empty] | Implement to Prod Complete
[5 empty] | \Outbound Analysis and Reporting\OAR 2016-04 | [61 empty] | Monitoring in Field
[5 empty] | \Outbound Analysis and Reporting\OAR 2016-05 | [61 empty] | Monitoring in the field
[5 empty] | \Performance Management Scorecard | [61 empty] | Not fixed
[5 empty] | \Performance Management Scorecard\PM 2015 | [61 empty] | Obsolete
[5 empty] | \Performance Management Scorecard\PM 2015\PM 2015-10 | [61 empty] | Pending customer direction
[5 empty] | \Performance Management Scorecard\PM 2015\PM 2015-11 | [61 empty] | Pending Dev & V&V
[5 empty] | \Performance Management Scorecard\PM 2015\PM 2015-12 | [61 empty] | Post Prod V&V Completed
[5 empty] | \Performance Management Scorecard\PM 2016 | [61 empty] | Regression
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-01 | [61 empty] | Test Failed
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-02 | [61 empty] | Verified
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-03 | [61 empty] | Waiting Customer Feedback
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-04 | [61 empty] | Waiting for external entity to complete work
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-05 | [61 empty] | Work completed
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-06 | [61 empty] | Closed
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-07 | [61 empty] | Code Complete - Test Passed - In BETA Test
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-08 | [61 empty] | Code Complete - Test Passed - In Customer Acceptance Test
[5 empty] | \Performance Management Scorecard\PM 2016\PM 2016-09 | [61 empty] | Code Complete and Testing Passed
[5 empty] | \Performance Management Scorecard\PM 2016-10 | [61 empty] | Implemented to Production
[5 empty] | \Performance Management Scorecard\PM 2016-11 | [61 empty] | Meeting was Held
[5 empty] | \Performance Management Scorecard\PM 2016-12 | [61 empty] | Task Completed/Close
[5 empty] | \Performance Management Scorecard\PM 2017-01 | [61 empty] | Validation Test Passed
[5 empty] | \Performance Management Scorecard\PM 2017-02 | [61 empty] | Accepted (as is)
[5 empty] | \Performance Management Scorecard\PM 2017-03 | [61 empty] | Accepted with Major Changes
[5 empty] | \Performance Management Scorecard\PM 2017-04 | [61 empty] | Accepted with Minor Changes
[5 empty] | \Performance Management Scorecard\PM 2017-05 | [61 empty] | Major Changes Complete
[5 empty] | \Performance Management Scorecard\PM Backlog | [61 empty] | Minor Changes Complete
[5 empty] | all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_System.IterationPath | [61 empty] | Accepted (won't mitigate)
Eliminated
Mitigated
Mitigation Action Complete
Mitigation Action Unsatisfactory (rework)
Mitigation Triggered
Admin Task V&V Complete
Administrative Task Complete
Administrative Task not Complete
Build & Compile Failed
Build & Compile Passed
Code Review Complete. Ready for Build & Compile
Code Review Failed
Complete and Does Not Require Review/Test
Data Quality Checks Completed
Dev and V&V Complete
Dev Complete. Ready for Build & Compile
Dev Complete. Ready for Code Review
Dev Server V&V
Intregration Test Complete
Pending Admin Task
Pending Data Quality Checks
Pending Development
Pending Planned Operational Activity
Pending Team Meeting
Performance Test Complete
Post Prod V&V
Post Prod V&V Complete
Production Server V&V
Production Server V&V Failed
Production Server V&V to be Completed
QA Server V&V
QA Server V&V Failed
Reactivated
Regression Test Complete
Research Task Completed
Submit Admin Task
Submit Data Quality Checks
Submit Dev and V&V
Submit Implementation
Submit Meeting Task
Submit Planned Operational Activity
Submit Server Maintenance
Submit V&V
System Test Complete
Unit Test Complete
User Acceptance Test Complete
V&V Complete
Verification and Validation Failed
Work Cancelled
Work Not Completed. Moving Remaining Work to the Next Iteration
Work Rejected/Cancelled
Completed
Update Test Case
all_VSTS_1537a096_c5ff_4c23_a187_872990c51753_System.Reason